{"text_format":"2","workbook":"xls","n_sheets":6,"sheets":["Ostatní mimo velká města ","Olomouc","Prostějov","Přerov","Suma nákladů","Jednotkové náklady"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":4,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Ostatní mimo velká města ","index":0,"n_rows":413,"n_cols":22,"rows_kept":413,"cut":false,"hidden":false,"merged":[[2,1,14,1],[101,1,106,1],[189,1,193,1],[304,1,308,1],[374,1,389,1],[163,1,181,1],[184,1,188,1],[312,1,316,1],[326,1,329,1],[210,1,215,1],[244,1,265,1],[289,1,303,1],[222,1,224,1],[330,1,334,1],[343,1,346,1],[42,1,55,1],[182,1,183,1],[194,1,209,1],[73,1,90,1],[266,1,288,1],[337,1,341,1],[391,1,395,1],[25,20,27,20],[91,1,100,1],[107,1,150,1],[16,1,30,1],[317,1,325,1],[347,1,351,1],[225,1,243,1],[0,0,0,21],[37,1,41,1],[56,1,65,1],[66,1,72,1],[151,1,162,1],[396,1,397,1],[370,1,372,1],[216,1,220,1],[25,21,27,21],[31,1,36,1],[412,14,412,16],[412,12,412,13],[400,1,403,1],[368,1,369,1],[352,1,367,1],[406,1,410,1],[411,14,411,16],[411,12,411,13],[398,1,399,1],[404,1,405,1]],"flags":["formulas_cached_only"]}
["Soupis připravených záměrů dle jednotlivých tras do roku 2018 s výhledem do roku 2022"]
[" č.","Trasa","Název akce","Obec","Katastrální území","Typ komunikace","ITI","IROP","SFDI","SPÚ","Lesy ČR","DUR / DSP","ST / IZ (pouze)","Délka          v km","Cena          mil. Kč         vč. DPH","Nákl. na  pozemky","Aktivita 2015","Aktivita 2016","Aktivita 2017","Aktivita 2018","Aktivita 2019-2022","Poznámka"]
[1,"A1","Smíšená stezka Nemilany - Kožušany","Kožušany - Tážany","Kožušany","C9","ano","ano","ano",null,null,"ano",null,0.098,0.577152576,null,null,null,"aktualizovat DÚR a zpracovat DSP+DPS","realizace"]
[2,null,"Smíšená stezka Nemilany - Kožušany","Kožušany - Tážany","Kožušany","B11",null,null,null,"ano",null,"ano",null,0.51,4.50532368,null,null,null,"aktualizovat DÚR a zpracovat DSP+DPS","realizace"]
[3,null,"Smíšená stezka Kožušany - Tážany - Blatec","Kožušany - Tážany","Kožušany, Tážany","C9","ano","ano","ano",{"$nulls":4},0.85,5.0059152,{"$nulls":5},"zpracovat PD a realizace"]
[4,null,"Smíšená stezka Kožušany - Tážany - Blatec","Blatec","Blatec","C9","ano","ano","ano",{"$nulls":4},0.9,5.3003808,{"$nulls":5},"zpracovat PD a realizace"]
[5,null,"Smíšená stezka Blatec - Vrbátky","Blatec","Blatec","C9","ano","ano","ano",{"$nulls":4},2.5,14.723279999999999,null,null,"zpracovat DUR","zpracovat DSP","realizace"]
[6,null,"Smíšená stezka Blatec - Vrbátky","Vrbátky","Vrbátky","C9","ano","ano","ano",{"$nulls":4},1.43,8.42171616,null,null,"zpracovat DUR","zpracovat DSP","realizace"]
[7,null,"Cyklostezka Olšany u Prostějova - Vrbátky","Olšany u Prostějova","Olšany u Prostějova","C9","ano","ano","ano",{"$nulls":4},0.48,2.8268697599999997,{"$nulls":5},"zpracovat PD a realizace","propojení větví A1 a A4 s vazbou na Lutín"]
[8,null,"Cyklostezka Olšany u Prostějova - Vrbátky","Olšany u Prostějova","Olšany u Prostějova, Hablov","B11",null,null,null,"ano",null,null,null,1.19,10.51242192,{"$nulls":5},"zpracovat PD a realizace"]
[9,null,"Cyklostezka Olšany u Prostějova - Vrbátky","Vrbátky","Dubany na Hané, Vrbátky","B11",null,null,null,"ano",null,null,null,1.87,16.51952016,{"$nulls":5},"zpracovat PD a realizace"]
[10,null,"Cyklostezka Olšany u Prostějova - Vrbátky","Vrbátky","Dubany na Hané","C9","ano","ano","ano",{"$nulls":4},0.15,0.8833967999999999,{"$nulls":5},"zpracovat PD a realizace"]
[11,null,"Smíšená stezka Vrbátky - Prostějov (Vrahovice)","Vrbátky","Vrbátky, Štětovice","C9","ano","ano","ano",null,null,null,"ano",1.59,9.36400608,null,null,"zpracovat DUR, DSP","realizace"]
[12,null,"Smíšená stezka Vrbátky - Prostějov (Vrahovice)","Prostějov","Čechůvky, Vrahovice","C9","ano","ano","ano",null,null,null,"ano",3,17.667935999999997,null,null,"zpracovat DUR, DSP","realizace"]
[13,null,"Chodník s povolením cyklistů Vrahovice","Prostějov","Vrahovice","C7+E13",{"$nulls":7},0.082,0.60365448,{"$nulls":5},"zpracovat PD a realizace"]
[14,"A1a","Smíšená stezka Olomouc-Nové Sady - Kožušany","Olomouc","Nové Sady u Olomouce, Nemilany","C9","ano","ano","ano",{"$nulls":4},2.29,13.486524479999998,{"$nulls":5},"zpracovat PD a realizace"]
[15,"A2","Lávka přes Týnečku na trase Holice-Grygov","Velký Týnec","Vsisko","Lávka","ano","ano","ano",{"$nulls":4},0.03,0.5,{"$nulls":5},"zpracovat PD a realizace"]
[16,null,"Cyklistická komunikace Holice - Grygov","Velký Týnec","Vsisko","B11",null,null,null,"ano",null,null,null,0.64,5.65373952,{"$nulls":5},"zpracovat PD a realizace"]
[17,null,"Cyklistická komunikace Holice - Grygov","Grygov","Grygov","B11",null,null,null,"ano",null,null,null,0.59,5.21204112,{"$nulls":5},"zpracovat PD a realizace"]
[18,null,"Cyklistická komunikace Grygov - Majetín","Grygov","Grygov","B11",null,null,null,"ano",null,null,null,0.35,3.091888799999999,{"$nulls":5},"zpracovat PD a realizace"]
[19,null,"Cyklistická komunikace Grygov - Majetín","Krčmaň","Krčmaň","B11",null,null,null,"ano",null,null,null,0.53,4.682003040000001,{"$nulls":5},"zpracovat PD a realizace"]
[20,null,"Cyklistická komunikace Grygov - Majetín","Majetín","Majetín","B11",null,null,null,"ano",null,null,null,1.25,11.042459999999998,{"$nulls":5},"zpracovat PD a realizace"]
[21,null,"Smíšená steka Brodek u Přerova, ul. Vrchlického","Brodek u Přerova","Brodek u Přerova","C9","ano","ano","ano",{"$nulls":4},0.29,2.1348756,{"$nulls":5},"zpracovat PD a realizace"]
[22,null,"Stezka pro chodce a cyklisty Brodek u Přerova, ul. Vrchlického","Brodek u Přerova","Brodek u Přerova","C10","ano","ano","ano",{"$nulls":4},0.17,1.6686384000000003,{"$nulls":5},"zpracovat PD a realizace"]
[23,null,"Chodník s povolením cyklistů Brodke u Přerova - podjezd pod železniční tratí na ul. 28. října","Brodek u Přerova","Brodek u Přerova","C7+E13","ano","ano","ano",{"$nulls":4},0.19,0.9324744,{"$nulls":5},"zpracovat PD a realizace"]
[24,null,"Smíšená steka Brodek u Přerova - Dub nad Moravou","Brodek u Přerova","Brodek u Přerova","C9","ano","ano","ano",{"$nulls":4},1.96,14.4288144,null,null,"zpracovat DUR","zpracovat DSP","realizace",null,"odbočná větev, významná vazba na terminál v Brodku, tři mostní objekty, nákladz na ně nejsou obsaženy v kalkulaci"]
[25,null,"Smíšená steka Brodek u Přerova - Dub nad Moravou","Citov","Citov","C9","ano","ano","ano",{"$nulls":4},0.2,1.1778624,null,null,"zpracovat DUR","zpracovat DSP","realizace"]
[26,null,"Smíšená steka Brodek u Přerova - Dub nad Moravou","Dub nad Moravou","Dub nad Moravou","C9","ano","ano","ano",{"$nulls":4},1.69,12.441171600000002,null,null,"zpracovat DUR","zpracovat DSP","realizace"]
[27,null,"Smíšená stezka Rokytnice - Luková","Brodek u Přerova","Luková u Přerova","C9","ano","ano","ano",null,null,"ano",null,0.64,3.769159679999999,null,null,null,"realizace"]
[28,null,"Smíšená stezka Rokytnice - Luková","Rokytnice","Rokytnice u Přerova","C9","ano","ano","ano",null,null,"ano",null,0.61,3.5924803199999995,null,null,null,"realizace"]
[29,null,"Přednádražní prostor - parkovací boxy","Brodek u Přerova",null,"Stojany","ano","ano",{"$nulls":4},"ano",null,2,null,null,"zpracování DSP, vydání SP","realizace"]
[30,"A2a","Vyhrazené jízdní pruhy Vsisko, ul. Olomoucká","Velký Týnec","Velký Týnec","V14+IP20","ano","ano","ano",{"$nulls":4},0.95,1.7242499999999998,{"$nulls":5},"zpracovat PD a realizace"]
[31,null,"Cyklistická komunikace Vsisko - Grygov","Velký Týnec","Vsisko","B11",null,null,null,"ano",null,null,null,2.29,20.22978672,{"$nulls":5},"zpracovat PD a realizace"]
[32,null,"Smíšená steka Velký Týnec- Grygov","Velký Týnec","Velký Týnec","C9","ano","ano","ano",{"$nulls":4},0.74,4.358090879999999,{"$nulls":5},"zpracovat PD a realizace","mimoúrovňové křížení s výhledovou R55"]
[33,null,"Smíšená steka Velký Týnec- Grygov","Grygov","Grygov","C9","ano","ano","ano",{"$nulls":4},0.39,2.29683168,{"$nulls":5},"zpracovat PD a realizace"]
[34,null,"Chodník s povolením cyklistů Velký Týnec - Čechovice","Velký Týnec","Velký Týnec, Čehovice","C7+E13","ano","ano","ano",{"$nulls":4},0.16,0.7852416000000001,{"$nulls":5},"zpracovat PD a realizace"]
[35,null,"Cyklostezka Velký Týnec – Čechovice","Velký Týnec","Velký Týnec, Čehovice","C9","ano","ano","ano",null,null,"ano",null,0.773,4.552438176,null,null,"realizace"]
[36,"A2b","Cyklistická komunikace Holice - Velký Týnec","Velký Týnec","Velký Týnec","B11",null,null,null,"ano",null,null,null,1.4,12.367555199999996,{"$nulls":5},"zpracovat PD a realizace"]
[37,null,"Cyklistická komunikace Velký Týnec - Krčmaň","Velký Týnec","Velký Týnec","B11",null,null,null,"ano",null,null,null,1.76,15.54778368,{"$nulls":5},"zpracovat PD a realizace"]
[38,null,"Cyklistická komunikace Velký Týnec - Krčmaň","Krčmaň","Krčmaň","B11",null,null,null,"ano",null,null,null,0.41,3.62192688,{"$nulls":5},"zpracovat PD a realizace"]
[39,null,"Smíšená stezka Krčmaň","Krčmaň","Krčmaň","C9","ano","ano","ano",{"$nulls":4},0.74,4.358090879999999,{"$nulls":5},"zpracovat PD a realizace"]
[40,null,"Chodník s povolením cyklistů Krčmaň","Krčmaň","Krčmaň","C7+E13","ano","ano","ano",{"$nulls":4},0.17,0.8343192000000001,{"$nulls":5},"zpracovat PD a realizace"]
[41,"A3","Smíšená steka Henčlov - Troubky","Přerov","Henčlov","C9","ano","ano","ano",{"$nulls":4},1.42,8.362823039999999,{"$nulls":5},"zpracovat PD a realizace"]
[42,null,"Smíšená steka Henčlov - Troubky","Troubky ","Troubky nad Bečvou","C9","ano","ano","ano",{"$nulls":4},1.72,10.12961664,{"$nulls":5},"zpracovat PD a realizace"]
[43,null,"Cyklistická komunikace Most přes Bečvu - Troubky","Tovačov","Tovačov","B11",{"$nulls":7},0.23,2.03181264,{"$nulls":5},"zpracovat PD a realizace"]
[44,null,"Cyklistická komunikace Most přes Bečvu - Troubky","Tovačov","Tovačov","C9","ano","ano","ano",{"$nulls":4},0.5,2.944656,{"$nulls":5},"zpracovat PD a realizace"]
[45,null,"Řešení cyklistů po mostech přes Bečvu a Moravu","Tovačov","Tovačov","C7+E13","ano","ano","ano",{"$nulls":4},0.28,1.3741728000000002,{"$nulls":5},"zpracovat PD a realizace"]
[46,null,"Cyklostezka Tovačov - Troubky","Tovačov","Tovačov","C9","ano","ano","ano",null,null,"ano",null,3.22,18.963584639999997,null,"zpracovaná RDS","realizace"]
[47,null,"Dělená stezka Tovačov, ul. Podvalí","Tovačov","Tovačov","C10","ano","ano","ano",{"$nulls":4},0.63,6.1837776,null,"zpracovává se studie","zpracování DSP","realizace"]
[48,null,"Dělená stezka Tovačov, ul. Prostějovská","Tovačov","Tovačov","C9","ano","ano","ano",{"$nulls":4},0.72,5.300380800000001,{"$nulls":5},"zpracovat PD a realizace"]
[49,null,"Smíšená steka Tovačov - Hrubčice","Tovačov","Tovačov","C9","ano","ano","ano",{"$nulls":4},3.22,18.963584639999997,{"$nulls":5},"zpracovat PD a realizace"]
[50,null,"Smíšená steka Tovačov - Hrubčice","Klopotovice","Klopotovice","C9","ano","ano","ano",{"$nulls":4},1,5.889312,{"$nulls":5},"zpracovat PD a realizace"]
[51,null,"Smíšená steka Tovačov - Hrubčice","Hrubčice","Hrubčice","C9","ano","ano","ano",{"$nulls":4},2.01,11.837517119999998,{"$nulls":5},"zpracovat PD a realizace"]
[52,null,"Vyhrazené jízdní pruhy Tovačov, ul. Olomoucká","Tovačov","Tovačov","C14+IP20","ano","ano","ano",{"$nulls":4},0.99,1.7968499999999998,null,"zpracová se studie","zpracovat DUR","zpracovat DSP","realizace"]
[53,null,"Smíšená steka Hrubčice - Kralice na Hané","Hrubčice","Hrubčice","C9","ano","ano","ano",{"$nulls":4},0.43,2.53240416,{"$nulls":5},"zpracovat PD a realizace"]
[54,null,"Smíšená steka Hrubčice - Kralice na Hané","Kralice na Hané","Kralice na Hané","C9","ano","ano","ano",{"$nulls":4},0.25,1.472328,{"$nulls":5},"zpracovat PD a realizace"]
[55,"A3a","Cyklistická komunikace Citov - Věrovany","Citov","Citov","B11",null,null,null,"ano",null,null,null,1.25,11.042459999999998,{"$nulls":5},"zpracovat PD a realizace"]
[56,null,"Cyklistická komunikace Citov - Věrovany","Věrovany","Věrovany","B11",null,null,null,"ano",null,null,null,0.47,4.151964959999999,{"$nulls":5},"zpracovat PD a realizace"]
[57,null,"Cyklistická komunikace Citov - Věrovany","Věrovany","Věrovany","C9","ano","ano","ano",{"$nulls":4},0.54,3.18022848,{"$nulls":5},"zpracovat PD a realizace"]
[58,null,"Cyklistická komunikace Citov - Věrovany","Věrovany","Věrovany","C14+IP20","ano","ano","ano",{"$nulls":4},0.08,0.5889312,{"$nulls":5},"zpracovat PD a realizace"]
[59,null,"Smíšená stezka Věrovany - Biskupice","Věrovany","Věrovany","C9","ano","ano","ano",{"$nulls":4},0.31,1.8256867199999998,{"$nulls":5},"zpracovat PD a realizace"]
[60,null,"Smíšená stezka Věrovany - Biskupice","Biskupice","Biskupice na Hané","C9","ano","ano","ano",{"$nulls":4},0.32,1.8845798399999996,{"$nulls":5},"zpracovat PD a realizace"]
[61,null,"Cyklistická komunikace Věrovany - Biskupice","Věrovany","Věrovany","B11",null,null,null,"ano",null,null,null,2.03,17.93295504,{"$nulls":5},"zpracovat PD a realizace"]
[62,null,"Cyklistická komunikace Věrovany - Biskupice","Biskupice","Biskupice na Hané","B11",null,null,null,"ano",null,null,null,0.31,2.7385300799999994,{"$nulls":5},"zpracovat PD a realizace"]
[63,null,"Smíšená stezka Kralice na Hané - Čechůvky","Kralice na Hané","Kralice na Hané","C9","ano","ano","ano",{"$nulls":4},0.73,4.299197759999999,{"$nulls":5},"zpracovat PD a realizace"]
[64,null,"Smíšená stezka Kralice na Hané - Čechůvky","Prostějov","Čechůvky","C9","ano","ano","ano",{"$nulls":4},0.4,2.3557248,{"$nulls":5},"zpracovat PD a realizace"]
[65,"A4","Smíšená stezka Hněvotín - průmyslová zóna","Hněvotín","Hněvotín","C9","ano","ano","ano",null,null,null,"ano",1.4,8.245036799999998,null,null,"zpracovat DUR / DSP","realizace"]
[66,null,"Cyklistická komunikace Hněvotín, Za humny","Hněvotín","Hněvotín","B11",{"$nulls":7},1,11.778624,{"$nulls":5},"zpracovat PD a realizace"]
[67,null,"Smíšená stezka Olšany - Hněvotín","Hněvotín","Hněvotín","C9","ano","ano","ano",null,null,null,"ano",1.25,7.3616399999999995,null,null,"zpracovat DUR / DSP","realizace"]
[68,null,"Smíšená stezka Olšany - Hněvotín","Olšany u Prostějova","Olšany u Prostějova","C9","ano","ano","ano",null,null,null,"ano",1.51,8.89286112,null,null,"zpracovat DUR / DSP","realizace"]
[69,null,"Stezka pro cyklisty Olšany - Držovice","Olšany u Prostějova","Olšany u Prostějova","C8","ano","ano","ano",{"$nulls":4},2.07,12.190875839999997,{"$nulls":5},"zpracovat PD a realizace"]
[70,null,"Stezka pro cyklisty Olšany - Držovice","Smržice","Smržice","C8","ano","ano","ano",{"$nulls":4},0.73,4.299197759999999,{"$nulls":5},"zpracovat PD a realizace"]
[71,null,"Stezka pro cyklisty Olšany - Držovice","Držovice","Držovice","C8","ano","ano","ano",{"$nulls":4},2.03,11.955303359999998,{"$nulls":5},"zpracovat PD a realizace"]
[72,"B1","Smíšená stezka Konice - Křemenec","Konice","Křemenec","C9","ano","ano","ano",{"$nulls":4},0.76,4.47587712,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[73,null,"Chodník s povolením cyklistů - Křemenec u zastávky","Konice","Křemenec","C7+E13","ano","ano","ano",{"$nulls":4},0.15,0.736164,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[74,null,"Smíšená stezka Křemenec - Čunín","Konice","Křemenec, Čunín","C9","ano","ano","ano",{"$nulls":4},1.13,6.654922559999999,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[75,null,"Chodník s povolením cyklistů - Čunín","Konice","Čunín","C7+E13","ano","ano","ano",{"$nulls":4},0.03,0.1472328,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[76,null,"Smíšená stezka Čunín (směr Maleny)","Konice","Čunín","C9","ano","ano","ano",{"$nulls":4},0.5,2.944656,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[77,null,"Smíšená stezka Maleny (směr Čunín)","Stražisko","Maleny","C9","ano","ano","ano",{"$nulls":4},0.15,0.8833967999999999,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[78,null,"Cyklistická komunikace Maleny","Stražisko","Maleny","B11",null,null,null,"ano",null,null,null,0.37,4.35809088,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[79,null,"Cyklistická komunikace Stražisko - Ptení","Stražisko","Stražisko","B11",null,null,null,"ano",null,null,null,0.16,1.88457984,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[80,null,"Cyklistická komunikace Stražisko - Ptení","Ptení","Ptení","B11",null,null,null,"ano",null,null,null,1.64,19.316943359999996,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[81,null,"Cyklistická komunikace Ptení - Zdětín, zastávka","Ptení","Ptení","B11",null,null,null,"ano",null,null,null,1.63,19.19915712,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[82,null,"Cyklistická komunikace Ptení - Zdětín, zastávka","Zdětín","Zdětín na Moravě","B11",null,null,null,"ano",null,null,null,1.53,18.02129472,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[83,null,"Cyklistická komunikace Zdětín, zastávka - Lutotín","Hluchov","Hluchov","C9","ano","ano","ano",{"$nulls":4},1.88,11.071906559999997,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[84,null,"Cyklistická komunikace Zdětín, zastávka - Lutotín","Bílovice-Lutotín","Lutotín","C9","ano","ano","ano",{"$nulls":4},0.12,0.7067174399999999,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[85,null,"Cyklistická komunikace Zdětín, zastávka - Lutotín","Bílovice-Lutotín","Lutotín","B11",null,null,null,"ano",null,null,null,1.16,13.663203839999998,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[86,null,"Smíšená stezka Lutotín, zastávka - Bílovice","Bílovice-Lutotín","Lutotín, Bílovice","C9","ano","ano","ano",{"$nulls":4},1.2,7.067174399999999,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[87,null,"Smíšená stezka Bílovice - Lutotín, propojka přes Romži","Bílovice-Lutotín","Lutotín, Bílovice","Lávka","ano","ano","ano",{"$nulls":4},0.053,0.5,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[88,null,"Cyklistická komunikace Bílovovice-Lutotín - Kostelec na Hané","Bílovice-Lutotín","Lutotín, Bílovice","B11",null,null,null,"ano",null,null,null,0.04,0.47114496,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[89,null,"Cyklistická komunikace Bílovovice-Lutotín - Kostelec na Hané","Kostelec na Hané","Kostelec na Hané","B11",null,null,null,"ano",null,null,null,0.53,6.2426707200000005,{"$nulls":5},"zpracovat PD a realizace","uvažuje se cca 1/2 k realizaci do r. 2018"]
[90,"B2","Smíšená stezka Nasobůrky, ul. Svatoplukova","Litovel","Nasobůrky","C9","ano","ano","ano",{"$nulls":4},0.77,4.534770239999999,{"$nulls":5},"zpracovat PD a realizace"]
[91,null,"Smíšená stezka Haňovice - Nasobůrky","Litovel","Nasobůrky","C9","ano","ano","ano",{"$nulls":4},0.11,0.6478243199999999,{"$nulls":5},"zpracovat PD a realizace"]
[92,null,"Smíšená stezka Haňovice - Nasobůrky","Haňovice","Haňovice","C9","ano","ano","ano",{"$nulls":4},0.59,3.47469408,{"$nulls":5},"zpracovat PD a realizace"]
[93,null,"Cyklistická komunikace Haňovice - Nová Ves","Haňovice","Haňovice","B11",null,null,null,"ano",null,null,null,1.03,9.09898704,{"$nulls":5},"zpracovat PD a realizace"]
[94,null,"Cyklistická komunikace Nová Ves - Savín","Litovel","Savín","B11",null,null,null,"ano",null,null,null,1.26,11.13079968,{"$nulls":5},"zpracovat PD a realizace"]
[95,null,"Smíšená stezka Savín - Slavětín","Litovel","Savín","C9","ano","ano","ano",{"$nulls":4},0.62,3.6513734399999995,{"$nulls":5},"zpracovat PD a realizace"]
[96,null,"Smíšená stezka Savín - Slavětín","Slavětín","Slavětín u Litovle","C9","ano","ano","ano",{"$nulls":4},0.45,2.6501904,{"$nulls":5},"zpracovat PD a realizace"]
[97,null,"Cyklistická komunikace Savín - Slavětín","Slavětín","Slavětín u Litovle","B11",{"$nulls":7},0.085,0.75088728,{"$nulls":5},"zpracovat PD a realizace"]
[98,null,"Cyklistická komunikace Ješov - Luká","Luká","Ješov","B11",null,null,null,"ano",null,"ano",null,1.09,9.629025120000001,{"$nulls":5},"zpracovat PD a realizace"]
[99,null,"Cyklistická komunikace Ješov - Luká","Luká","Luká","C9","ano","ano","ano",null,null,"ano",null,0.71,4.181411519999999,{"$nulls":5},"zpracovat PD a realizace"]
[100,"B2a","Smíšená stezka Slavětín - Veselíčko","Slavětín","Slavětín u Litovle","C9","ano","ano","ano",{"$nulls":4},1.4,8.245036799999998,{"$nulls":5},"zpracovat PD a realizace"]
[101,null,"Smíšená stezka Slavětín - Veselíčko","Luká","Veselíčko","C9","ano","ano","ano",{"$nulls":4},0.29,1.7079004799999995,{"$nulls":5},"zpracovat PD a realizace"]
[102,null,"Cyklistická komunikace Javoříčko - Vojtěchov","Luká ","Javoříčko, Březika","B11",{"$nulls":4},"ano",null,null,2.69,31.68449856,{"$nulls":5},"zpracovat PD a realizace"]
[103,null,"Cyklistická komunikace Javoříčko - Vojtěchov","Hvozd","Vojtěchov u Konice","B11",{"$nulls":4},"ano",null,null,0.59,6.94938816,{"$nulls":5},"zpracovat PD a realizace"]
[104,null,"Cyklistická komunikace Hvozd u Konice - Ponikev","Hvozd","Hvozd u Konice","C9","ano","ano","ano",{"$nulls":4},0.95,5.594846399999999,{"$nulls":5},"zpracovat PD a realizace"]
[105,null,"Cyklistická komunikace Hvozd u Konice - Ponikev","Hvozd","Hvozd u Konice","B11",null,null,null,"ano",null,null,null,0.27,2.38517136,{"$nulls":5},"zpracovat PD a realizace"]
[106,"B3","Vyhrazené jízdní pruhy Litovel, ul. Dukelská","Litovel","Litovel","V14+IP20","ano","ano","ano",{"$nulls":4},1.25,9.202050000000002,{"$nulls":5},"zpracovat PD a realizace"]
[107,null,"Cyklistická komunikace Nasobůrky - Haňovice - Myslechovice","Litovel","Litovel, Nasobůrky","B11",null,null,null,"ano",null,null,null,1.06,9.364006080000001,{"$nulls":5},"zpracovat PD a realizace"]
[108,null,"Cyklistická komunikace Nasobůrky - Haňovice - Myslechovice","Haňovice","Haňovice","B11",null,null,null,"ano",null,null,null,0.42,3.71026656,{"$nulls":5},"zpracovat PD a realizace"]
[109,null,"Cyklistická komunikace Nasobůrky - Haňovice - Myslechovice","Haňovice","Haňovice","C9","ano","ano","ano",{"$nulls":4},0.52,3.0624422399999998,{"$nulls":5},"zpracovat PD a realizace"]
[110,null,"Cyklistická komunikace Nasobůrky - Haňovice - Myslechovice","Litovel","Myslechovice","C9","ano","ano","ano",{"$nulls":4},0.22,1.2956486399999998,{"$nulls":5},"zpracovat PD a realizace"]
[111,null,"Cyklistická komunikace Myslechovice, nádražní","Litovel","Myslechovice","B11",{"$nulls":7},0.085,0.75088728,{"$nulls":5},"zpracovat PD a realizace"]
[112,null,"Cyklistická komunikace Myslechovice - Cholina - Odrlice - Senice na Hané","Litovel","Myslechovice","C9","ano","ano","ano",{"$nulls":4},1.06,6.2426707200000005,{"$nulls":5},"zpracovat PD a realizace"]
[113,null,"Cyklistická komunikace Myslechovice - Cholina - Odrlice - Senice na Hané","Cholina","Cholina","B11",null,null,null,"ano",null,null,null,2.16,19.08137088,{"$nulls":5},"zpracovat PD a realizace"]
[114,null,"Cyklistická komunikace Myslechovice - Cholina - Odrlice - Senice na Hané","Senice na Hané","Odrlice","B11",null,null,null,"ano",null,null,null,1.65,14.576047199999998,{"$nulls":5},"zpracovat PD a realizace"]
[115,null,"Cyklistická komunikace Myslechovice - Cholina - Odrlice - Senice na Hané","Senička","Senička","C9","ano","ano","ano",{"$nulls":4},0.79,4.65255648,{"$nulls":5},"zpracovat PD a realizace"]
[116,null,"Smíšená stezka Dubčany - Senice na Hané","Dubčany","Dubčany u Choliny","C9","ano","ano","ano",{"$nulls":4},0.78,4.59366336,{"$nulls":5},"zpracovat PD a realizace"]
[117,null,"Smíšená stezka Dubčany - Senice na Hané","Senice na Hané","Odrlice","C9","ano","ano","ano",{"$nulls":4},0.32,1.8845798399999996,{"$nulls":5},"zpracovat PD a realizace"]
[118,null,"Smíšená stezka Dubčany - Senice na Hané","Senička","Senička","C9","ano","ano","ano",{"$nulls":4},0.81,4.7703427199999995,{"$nulls":5},"zpracovat PD a realizace"]
[119,null,"Chodník s povolením cyklistů Senice na Hané - zastávka","Senice na Hané","Senice na Hané","C7+E13",{"$nulls":7},0.29,0.1,{"$nulls":5},"zpracovat PD a realizace"]
[120,null,"Cyklistická komunikace Senice na Hané - Náměšť na Hané","Senice na Hané","Senice na Hané","C9","ano","ano","ano",{"$nulls":4},0.39,2.29683168,{"$nulls":5},"zpracovat PD a realizace"]
[121,null,"Cyklistická komunikace Senice na Hané - Náměšť na Hané","Náměšť na Hané","Náměšť na Hané","C9","ano","ano","ano",{"$nulls":4},0.97,5.71263264,{"$nulls":5},"zpracovat PD a realizace"]
[122,null,"Cyklistická komunikace Senice na Hané - Náměšť na Hané","Náměšť na Hané","Náměšť na Hané","B11",null,null,null,"ano",null,null,null,0.44,3.88694592,{"$nulls":5},"zpracovat PD a realizace"]
[123,null,"Cyklistická komunikace Senice na Hané - Náměšť na Hané","Náměšť na Hané","Náměšť na Hané","C9","ano","ano","ano",{"$nulls":4},0.62,3.6513734399999995,{"$nulls":5},"zpracovat PD a realizace"]
[124,null,"Cyklistická komunikace Drahanovice - Náměšť na Hané","Náměšť na Hané","Náměšť na Hané","B11",null,null,null,"ano",null,null,"ano",1.54,13.604310719999999,null,null,"zpracovat DUR","zpracovat DSP","realizace"]
[125,null,"Cyklistická komunikace Drahanovice - Náměšť na Hané","Drahanovice","Drahanovice","B11",null,null,null,"ano",null,null,"ano",0.63,5.56539984,null,null,"zpracovat DUR","zpracovat DSP","realizace"]
[126,null,"Chodník s povolením cyklistů Drahanovice","Drahanovice","Drahanovice","C7+E13","ano","ano",{"$nulls":5},1.03,5.0549928,{"$nulls":5},"zpracovat PD a realizace"]
[127,null,"Smíšená stezka Ludéřov- Drahanovice","Drahanovice","Drahanovice, Ludéřov","C9","ano","ano","ano",null,null,null,"ano",0.7,4.122518399999999,{"$nulls":5},"zpracovat PD a realizace"]
[128,null,"Cyklistická komunikace Drahanovice - Slatinice na Hané","Drahanovice","Drahanovice","C9","ano","ano","ano",{"$nulls":4},0.93,5.47706016,{"$nulls":5},"zpracovat PD a realizace"]
[129,null,"Cyklistická komunikace Drahanovice - Slatinice na Hané","Tešetice","Rataje u Olomouce","C9","ano","ano","ano",{"$nulls":4},0.47,2.767976639999999,{"$nulls":5},"zpracovat PD a realizace"]
[130,null,"Cyklistická komunikace Drahanovice - Slatinice na Hané","Slatinice","Slatinice na Hané","C9","ano","ano","ano",{"$nulls":4},0.25,1.472328,{"$nulls":5},"zpracovat PD a realizace"]
[131,null,"Cyklistická komunikace Drahanovice - Slatinice na Hané","Slatinice","Slatinice na Hané","B11",null,null,null,"ano",null,null,null,1.23,10.865780639999999,{"$nulls":5},"zpracovat PD a realizace"]
[132,null,"Smíšená stezka Slatinice na Hané podél dráhy","Slatinice","Slatinice na Hané","C9","ano","ano","ano",{"$nulls":4},1.22,7.184960639999999,{"$nulls":5},"zpracovat PD a realizace"]
[133,null,"Cyklistická komunikace  Slatinice - Lutín","Slatinice","Slatinice na Hané","C9","ano","ano","ano",null,null,null,"ano",0.65,3.8280528,null,null,"zpracování DUR, vydání ÚR","zpracování DSP, vydání SP","realizace"]
[134,null,"Cyklistická komunikace  Slatinice - Lutín","Slatinice","Slatinice na Hané","B11",null,null,null,"ano",null,null,"ano",0.25,2.208492,null,null,"zpracování DUR, vydání ÚR","zpracování DSP, vydání SP","realizace"]
[135,null,"Cyklistická komunikace  Slatinice - Lutín","Lutín","Lutín","C9","ano","ano","ano",null,null,null,"ano",0.71,4.181411519999999,null,null,"zpracování DUR, vydání ÚR","zpracování DSP, vydání SP","realizace"]
[136,null,"Cyklistická komunikace  Slatinice - Lutín","Lutín","Lutín","B11",null,null,null,"ano",null,null,"ano",0.42,3.71026656,null,null,"zpracování DUR, vydání ÚR","zpracování DSP, vydání SP","realizace"]
[137,null,"Dělená stezka Lutín, ul. Školní","Lutín","Lutín","C10","ano","ano","ano",{"$nulls":4},0.222,2.1790454400000003,null,null,"zpracování DUR, vydání ÚR","zpracování DSP, vydání SP","realizace"]
[138,null,"Cyklostezka Lutín - Třebčín","Lutín","Lutín, Třebčín","C9","ano","ano","ano",null,null,"ano",null,1.24,7.302746879999999,null,"zpracovává se DUR / DSP","realizace"]
[139,null,"Cyklistická komunikace Slatinice - Třebčín","Slatinice","Slatinice na Hané","B11",null,null,null,"ano",null,null,null,0.27,2.38517136,{"$nulls":5},"zpracovat PD a realizace"]
[140,null,"Cyklistická komunikace Slatinice - Třebčín","Lutín","Třebčín","B11",null,null,null,"ano",null,null,null,0.32,2.82686976,{"$nulls":5},"zpracovat PD a realizace"]
[141,null,"Smíšená stezka Třebčín na průtahu silnice III. Třídy","Lutín","Třebčín","C9","ano","ano","ano",{"$nulls":4},0.26,1.9140264000000002,{"$nulls":5},"zpracovat PD a realizace"]
[142,null,"Cyklistická komunikace Třebčín směr Kaple","Lutín","Třebčín","B11",null,null,null,"ano",null,null,null,0.93,8.21559024,{"$nulls":5},"zpracovat PD a realizace"]
[143,null,"Cyklistická komunikace Třebčín směr Kaple","Slatinky","Slatinky","C9","ano","ano","ano",{"$nulls":4},0.96,5.653739519999999,{"$nulls":5},"zpracovat PD a realizace"]
[144,null,"Cyklistická komunikace Třebčín směr Kaple","Čelechovice na Hané","Čelechovice na Hané","C9","ano","ano","ano",{"$nulls":4},0.22,1.2956486399999998,{"$nulls":5},"zpracovat PD a realizace"]
[145,null,"Cyklistická komunikace Kaple - Čelechovice na Hané","Čelechovice na Hané","Čelechovice na Hané","C9","ano","ano","ano",{"$nulls":4},0.34,2.00236608,{"$nulls":5},"zpracovat PD a realizace"]
[146,null,"Cyklistická komunikace Kaple - Čelechovice na Hané","Čelechovice na Hané","Čelechovice na Hané","B11",null,null,null,"ano",null,null,null,1.47,12.98593296,{"$nulls":5},"zpracovat PD a realizace"]
[147,null,"Smíšená stezka  Čelechovice - Smržice","Čelechovice na Hané","Čelechovice na Hané","C9","ano","ano","ano",{"$nulls":4},0.45,2.6501904,{"$nulls":5},"zpracovat PD a realizace"]
[148,null,"Smíšená stezka  Čelechovice - Smržice","Smržice","Smržice","C9","ano","ano","ano",{"$nulls":4},0.49,2.8857628799999997,{"$nulls":5},"zpracovat PD a realizace"]
[149,null,"Smíšená stezka Smržice, ul. Za Farskou, Příční","Smržice","Smržice","C9","ano","ano","ano",{"$nulls":4},0.2,1.4723280000000003,{"$nulls":5},"zpracovat PD a realizace"]
[150,"B3a","Cyklistická komunikace Odrlice směr Senička","Senice na Hané","Odrlice","B11",null,null,null,"ano",null,null,null,0.61,5.38872048,{"$nulls":5},"zpracovat PD a realizace"]
[151,null,"Smíšená stezka Odrlice - Senička","Senice na Hané","Odrlice","C9","ano","ano","ano",{"$nulls":4},0.04,0.23557247999999995,{"$nulls":5},"zpracovat PD a realizace"]
[152,null,"Smíšená stezka Odrlice - Senička","Senička","Senička","C9","ano","ano","ano",{"$nulls":4},0.52,3.0624422399999998,{"$nulls":5},"zpracovat PD a realizace"]
[153,null,"Cyklistická komunikace Náměšť na Hané - Senička","Senička","Senička","B11",null,null,null,"ano",null,null,"ano",0.79,6.97883472,null,null,"zpracovat DSP","realizace"]
[154,null,"Cyklistická komunikace Náměšť na Hané - Senička","Senice na Hané","Senice na Hané","B11",null,null,null,"ano",null,null,"ano",0.76,6.713815680000001,null,null,"zpracovat DSP","realizace"]
[155,null,"Cyklistická komunikace Náměšť na Hané - Senička","Náměšť na Hané","Náměšť na Hané","B11",null,null,null,"ano",null,null,"ano",1.24,10.954120319999998,null,null,"zpracovat DSP","realizace"]
[156,null,"Cyklostezka Drahanovice - Slatinice na Hané - Západ","Drahanovice","Drahanovice","B11",null,null,null,"ano",null,null,null,1.18,10.42408224,{"$nulls":5},"zpracovat PD a realizace"]
[157,null,"Cyklostezka Drahanovice - Slatinice na Hané - Západ","Slatinice","Slatinice na Hané","B11",null,null,null,"ano",null,null,null,0.77,6.8021553599999995,{"$nulls":5},"zpracovat PD a realizace"]
[158,null,"Smíšená stezka Slatinice na Hané podél II/449 extravilán","Slatinice","Slatinice na Hané","C9","ano","ano","ano",{"$nulls":4},0.48,2.8268697599999997,{"$nulls":5},"zpracovat PD a realizace"]
[159,null,"Stezka pro chodce a cyklisty dělená, Slatinice na Hané, ke hřbitovu","Slatinice","Slatinice na Hané","C10","ano","ano","ano",{"$nulls":4},0.33,3.2391216000000003,{"$nulls":5},"zpracovat PD a realizace"]
[160,null,"Stezka pro cyklistky Slatinice na Hané","Slatinice","Slatinice na Hané, Lípy","C8","ano","ano","ano",{"$nulls":4},0.062,0.45642168000000005,{"$nulls":5},"zpracovat PD a realizace","přebudování stávajícího schodiště na rampu"]
[161,null,"Cyklistická komunikace Třebčín (od Líp po Kaplickou)","Lutín","Třebčín","B11",{"$nulls":7},0.9,7.950571200000001,{"$nulls":5},"zpracovat PD a realizace"]
[162,"B4","Cyklistická komunikace Mohelnice (směr Újezd) - pod R35","Mohelnice","Mohelnice","C8","ano","ano","ano",{"$nulls":4},0.1,0.7361640000000002,{"$nulls":5},"zpracovat PD a realizace"]
[163,null,"Smíšená stezka Mohelnice jih, křížení z ul. Olomoucké s II/444","Mohelnice","Mohelnice","C9","ano","ano","ano",{"$nulls":4},0.27,1.9876428000000004,{"$nulls":5},"zpracovat PD a realizace"]
[164,null,"Cyklostezka Mohelnice - Moravičany","Mohelnice","Mohelnice","B11",null,null,null,"ano",null,null,null,1.3,11.4841584,{"$nulls":5},"zpracovat PD a realizace"]
[165,null,"Cyklistická komunikace Moravičany - Mladeč","Moravičany","Moravičany, Doubravice nad Moravou","B11",null,null,null,"ano",null,null,null,2.54,22.43827872,{"$nulls":5},"zpracovat PD a realizace"]
[166,null,"Cyklistická komunikace Moravičany - Mladeč","Palonín","Palonín","B11",null,null,null,"ano",null,null,null,1,8.833968,{"$nulls":5},"zpracovat PD a realizace"]
[167,null,"Cyklistická komunikace Moravičany - Mladeč","Bílá Lhota","Řimice","B11",null,null,null,"ano",null,null,null,1.94,17.13789792,{"$nulls":5},"zpracovat PD a realizace"]
[168,null,"Cyklistická komunikace Moravičany - Mladeč","Mladeč","Mladeč","B11",null,null,null,"ano",null,null,null,1.6,14.134348800000001,{"$nulls":5},"zpracovat PD a realizace"]
[169,null,"Cyklistická komunikace Moravičany - Loštice ZD","Moravičany","Moravičany","B11",null,null,null,"ano",null,null,null,1.63,14.399367839999998,{"$nulls":5},"zpracovat PD a realizace"]
[170,null,"Smíšená stezka Loštice kolem Třebůvky","Loštice","Loštice","C9","ano","ano","ano",{"$nulls":4},0.97,5.71263264,{"$nulls":5},"zpracovat PD a realizace"]
[171,null,"Smíšená stetka Moravičany - Doubravice","Moravičany","Moravičany","C9","ano","ano","ano",{"$nulls":4},0.59,3.47469408,{"$nulls":5},"zpracovat PD a realizace"]
[172,null,"Cyklistická komunikace Doubravice - Mitrovice","Moravičany","Moravičany","B11",null,null,null,"ano",null,null,null,0.79,6.97883472,{"$nulls":5},"zpracovat PD a realizace"]
[173,null,"Smíšená stezka Doubravice - Řimice","Moravičany","Doubravice nad Moravou","C9","ano","ano","ano",{"$nulls":4},0.6,3.5335871999999995,{"$nulls":5},"zpracovat PD a realizace"]
[174,null,"Smíšená stezka Doubravice - Řimice","Palonín","Palonín","C9","ano","ano","ano",{"$nulls":4},0.38,2.23793856,{"$nulls":5},"zpracovat PD a realizace"]
[175,null,"Smíšená stezka Doubravice - Řimice","Bílá Lhota","Řimice","C9","ano","ano","ano",{"$nulls":4},1.45,8.5395024,{"$nulls":5},"zpracovat PD a realizace"]
[176,null,"Smíšená stezka Loštice - Žadlovice","Loštice","Loštice, Žadlovice","C9","ano","ano","ano",{"$nulls":4},0.62,3.6513734399999995,{"$nulls":5},"zpracovat PD a realizace"]
[177,null,"Smíšená stezka Loštice ul. Olomoucká","Loštice","Loštice","C9","ano","ano","ano",{"$nulls":4},0.58,3.415800959999999,{"$nulls":5},"zpracovat PD a realizace"]
[178,null,"Cyklistická komunikace Loštice, ul. Palonínská","Loštice","Loštice","B11",{"$nulls":7},0.41,3.62192688,{"$nulls":5},"zpracovat PD a realizace"]
[179,null,"CS Palonín – Loštice","Loštice","Loštice","C9","ano","ano","ano",null,null,"ano",null,0.3,1.1778623999999998,null,"aktualizovat DUR","zpracovat DSP","realizace"]
[180,null,"CS Palonín – Loštice","Palonín","Palonín","C9","ano","ano","ano",null,null,"ano",null,0.63,2.47351104,null,"aktualizovat DUR","zpracovat DSP","realizace"]
[181,"B5","Vyhrazené jízdní pruhy Mohelnice, ul. Družstevní","Mohelnice","Mohelnice","V14+IP20","ano","ano","ano",{"$nulls":4},0.98,1.7787,{"$nulls":5},"zpracovat PD a realizace"]
[182,null,"Smíšená steka Mohelnice - Stavenice","Mohelnice","Mohelnice","C9","ano","ano","ano",{"$nulls":4},1.97,11.60194464,{"$nulls":5},"zpracovat PD a realizace"]
[183,"B6","Stezka pro chodce a cyklisty dělená Litovel, ul. Uničovská","Litovel","Litovel","C10","ano","ano","ano",{"$nulls":4},0.46,4.5151392,null,null,"zpracovat DUR / DSP","realizace"]
[184,null,"Chodník s povolením cyklistů Litovel, ul. Uničovská","Litovel","Litovel","C7+E13","ano","ano",{"$nulls":5},0.34,1.6686384000000003,null,null,"zpracovat DUR / DSP","realizace"]
[185,null,"Smíšená stezka Litovel - Červenka","Červenka","Červenka","C9","ano","ano","ano",null,null,null,"ano",1.51,8.89286112,null,null,"zpracovat DUR / DSP","realizace"]
[186,null,"Smíšená stezka Červenka - Střelice","Červenka","Červenka","C9","ano","ano","ano",{"$nulls":4},0.677,3.9870642239999996,{"$nulls":5},"zpracovat PD a realizace"]
[187,null,"Smíšená stezka Červenka - Střelice","Uničov","Střelice u Uničova","C9","ano","ano","ano",{"$nulls":4},1.72,10.12961664,{"$nulls":5},"zpracovat PD a realizace"]
[188,"B7","Stezka pro chodce a cyklisty Šternberk – Uničov","Uničov","Brníčko a Želechovice u Uničova","C9","ano","ano","ano",null,null,"ano",null,1.26,6.183777599999999,null,"aktualizace DSP a vydání SP","realizace"]
[189,null,"Stezka pro chodce a cyklisty Šternberk – Uničov, úsek Mladějovice - Újezd","Mladějovice","Mladějovice u Šternberka","C9","ano","ano","ano",null,null,"ano",null,1.74,8.5395024,{"$nulls":5},"zpracovat PD a realizace"]
[190,null,"Stezka pro chodce a cyklisty Šternberk – Uničov, úsek Mladějovice - Babice","Mladějovice","Mladějovice u Šternberka","C9","ano","ano","ano",null,null,"ano",null,1.37,6.7236312,null,null,"aktualizace DSP a vydání SP","realizace"]
[191,null,"Stezka pro chodce a cyklisty Šternberk – Uničov, k.ú. Babice u Šternberka","Babice","Babice u Šternberka","C9","ano","ano","ano",null,null,"ano",null,1.021,5.01082296,null,null,"aktualizace DSP a vydání SP","realizace"]
[192,null,"Smíšená stezka ul. Věžní","Šternberk","Šternberk","C10","ano","ano","ano",null,null,null,"ano",0.83,8.1468816,null,null,"uplatňováno v rámci zpracování PD rekonstrukce silnice",null,"realizace"]
[193,"B8","Cyklostezka Litovel - Tři Dvory podél silnice II/447","Litovel","Litovel. Červenka, Tři Dvory u Litovle","C9","ano","ano","ano",null,null,"ano",null,1.8,10.6007616,null,"zpracovává se DUR","vydání ÚR","zpracování DSP, vydání SP","realizace"]
[194,null,"Smíšená stezka Tři Dvory - Pňovice","Litovel","Tři Dvory u Litovle","C9","ano","ano","ano",{"$nulls":4},1.2,7.067174399999999,{"$nulls":5},"zpracovat PD a realizace"]
[195,null,"Smíšená stezka Tři Dvory - Pňovice","Pňovice","Pňovice","C9","ano","ano","ano",{"$nulls":4},2.07,12.190875839999997,{"$nulls":5},"zpracovat PD a realizace"]
[196,null,"Smíšená stezka Pňovice - Žerotín","Pňovice","Pňovice","C9","ano","ano","ano",{"$nulls":4},0.68,4.00473216,{"$nulls":5},"zpracovat PD a realizace"]
[197,null,"Smíšená stezka Pňovice - Žerotín","Žerotín","Žerotín","C9","ano","ano","ano",{"$nulls":4},0.5,2.944656,{"$nulls":5},"zpracovat PD a realizace"]
[198,null,"Smíšená stezka Žerotín, průtah obcí II/447","Žerotín","Žerotín","C9","ano","ano","ano",{"$nulls":4},1.21,7.1260675199999985,{"$nulls":5},"zpracovat PD a realizace"]
[199,null,"Cyklistická komunikace Žerotín - Hnojice","Žerotín","Žerotín","B11",null,null,null,"ano",null,null,null,1.2,10.600761599999998,{"$nulls":5},"zpracovat PD a realizace"]
[200,null,"Cyklistická komunikace Žerotín - Hnojice","Liboš","Liboš","B11",null,null,null,"ano",null,null,null,0.71,6.27211728,{"$nulls":5},"zpracovat PD a realizace"]
[201,null,"Smíšená stezka Hnojice - Žerotín","Hnojice","Hnojice","C9","ano","ano","ano",{"$nulls":4},0.26,1.5312211199999999,{"$nulls":5},"zpracovat PD a realizace"]
[202,null,"Smíšená stezka Hnojice - Stádlo - Lužice","Hnojice","Hnojice","C9","ano","ano","ano",{"$nulls":4},1.22,7.184960639999999,{"$nulls":5},"zpracovat PD a realizace"]
[203,null,"Smíšená stezka Hnojice - Stádlo - Lužice","Lužice","Lužice u Šternberka","C9","ano","ano","ano",{"$nulls":4},1.19,7.008281279999999,{"$nulls":5},"zpracovat PD a realizace"]
[204,null,"Cyklistická komunikace Lužice směr Stádlo","Lužice","Lužice u Šternberka","B11",{"$nulls":7},0.17,1.50177456,{"$nulls":5},"zpracovat PD a realizace"]
[205,null,"Smíšená stezka na průtahu II/447 obcí Lužice","Lužice","Lužice u Šternberka","C9","ano","ano","ano",{"$nulls":4},0.53,3.1213353600000002,{"$nulls":5},"zpracovat PD a realizace"]
[206,null,"Chodník s povolením cyklistů Šternberk, ul. Pískoviště","Šternberk","Šternberk","C7+E13","ano","ano",{"$nulls":5},0.08,0.39262080000000005,{"$nulls":5},"zpracovat PD a realizace"]
[207,null,"Smíšená stezka Šternberk, ul. Nábřežní","Šternberk","Šternberk","C9","ano","ano","ano",{"$nulls":4},0.32,1.8845798399999996,{"$nulls":5},"zpracovat PD a realizace"]
[208,null,"Stezka pro chodce a cyklisty Šternberk, ul. Nádražní","Šternberk","Šternberk","C10","ano","ano","ano",{"$nulls":4},0.51,5.0059152000000005,{"$nulls":5},"zpracovat PD a realizace"]
[209,"B9","Propojení ul. Lhotská a stezky do Štarnova","Šternberk",null,"C8","ano","ano","ano",null,null,null,"ano",0.225,1.3803075,null,null,"zadání DUR","zpracování DSP, vydání SP","realizace"]
[210,null,"Propojení ul. Lhotská s přednádražním prostorem","Šternberk",null,"C10","ano","ano","ano",null,null,null,"ano",0.295,2.8955783999999998,null,null,"zadání DUR","zpracování DSP, vydání SP","realizace"]
[211,null,"Přednádražní prostor - parkovací boxy","Šternberk",null,"Stojany","ano","ano",{"$nulls":4},"ano",null,2,null,null,null,"zpracování DSP, vydání SP","realizace"]
[212,null,"Převedení cyklistů pod mostem ev.č. 4468-1","Štarnov",null,"C9","ano","ano","ano",null,null,null,"ano",0.3,1.7667935999999997,null,"zadána DUR / DSP","realizace"]
[213,null,"Přednádražní prostor - parkovací boxy","Bohuňovice",null,"Stojany","ano","ano",{"$nulls":4},"ano",null,1,null,null,"zpracování DSP, vydání SP","realizace"]
[214,null,"Smíšená stezka k nádraží Bohuňovice","Bohuňovice","Bohuňovice","C9","ano","ano","ano",{"$nulls":4},0.2,1.1778624,{"$nulls":5},"zpracovat PD a realizace"]
[215,"B10","Stezka pro chodce a cyklisty Náklo - Mezice","Náklo","Náklo","C9","ano","ano",null,null,null,"ano",null,0.57,4.196134799999999,null,"zpracovaná DUR / DSP","vydání UR / SP","realizace"]
[216,null,"Cyklistická komunikace Příkazy směr Skrbeň k železniční trati","Příkazy","Příkazy","B11",null,null,null,"ano",null,null,null,0.36,3.1802284800000002,{"$nulls":5},"zpracovat PD a realizace"]
[217,null,"Smíšená stezka Příkazy - Skrbeň","Příkazy","Příkazy","C9","ano","ano","ano",{"$nulls":4},0.85,5.0059152,{"$nulls":5},"zpracovat PD a realizace"]
[218,null,"Smíšená stezka Příkazy - Skrbeň","Skrbeň","Skrbeň","C9","ano","ano","ano",{"$nulls":4},0.38,2.23793856,{"$nulls":5},"zpracovat PD a realizace"]
[219,null,"Smíšená stezka Horka nad Moravou - hranice k.ú. Skrbeň","Horka nad Moravou","Horka nad Moravou","C9","ano","ano","ano",null,null,null,"ano",0.546,3.215564352,null,"zpracovává se studie","zpracování DUR, vydání ÚR","zpracování DSP, vydání SP","realizace"]
[220,"B11","Cyklistická komunikace Břuchotín na trase 51A","Křelov-Břuchotín","Břuchotín","B11",null,null,null,"ano",null,null,null,0.27,2.38517136,{"$nulls":5},"zpracovat PD a realizace"]
[221,"B13","Smíšená stezka Velká Bystřice, ul. U Konírny - ul. Zámecká","Velká Bystřice","Velká Bystřice","C9","ano","ano","ano",null,null,null,"ano",0.435,2.5618507199999994,null,"zadána DUR","zpracování DSP, vydání SP","realizace"]
[222,null,"Cyklistická komunikace Velká Bystřice, ul. Za parkem","Velká Bystřice","Velká Bystřice","B11",{"$nulls":7},0.8,7.067174400000001,{"$nulls":5},"zpracovat PD a realizace"]
[223,null,"Odvedení cyklistů z MK Ul. U Sušírny","Bystrovany",null,"C9","ano","ano","ano",null,null,"ne","ano",0.805,4.740896159999999,null,null,"zpracování DUR, vydání ÚR","zpracování DSP, vydání SP","realizace"]
[224,"B14","Vyhrazené jízdní pruhy Velká Bystřice ul. ČSA, část","Velká Bystřice","Velká Bystřice","V14+IP20","ano","ano","ano",null,null,null,"ano",0.19,1.3987116000000004,{"$nulls":5},"zpracovat PD a realizace"]
[225,null,"Propojení pro cyklisty mimo silnici III/03554 ve Velkém Újezdu","Velký Újezd","Velký Újezd","C9","ano","ano","ano",null,null,"ano",null,0.33,1.9434729599999998,null,"zadána DUR / DSP","realizace"]
[226,null,"Cyklistická komunikace Velký Újezd - Staměřice, část Velký Újezd","Velký Újezd","Velký Újezd","C8","ano","ano","ano",{"$nulls":4},0.75,4.416983999999999,{"$nulls":5},"zpracovat PD a realizace"]
[227,null,"Cyklistická komunikace Velký Újezd - Staměřice, část po samotu","Dolní Újezd","Staměřice","C8","ano","ano","ano",{"$nulls":4},0.31,1.8256867199999998,{"$nulls":5},"zpracovat PD a realizace"]
[228,null,"Cyklistická komunikace Velký Újezd - Staměřice, část sjezdku k samotě","Dolní Újezd","Staměřice","B11",{"$nulls":7},0.14,1.2367555200000002,{"$nulls":5},"zpracovat PD a realizace"]
[229,null,"Cyklistická komunikace Velký Újezd - Staměřice, část extravilán Staměřice","Dolní Újezd","Staměřice","C8","ano","ano","ano",{"$nulls":4},0.61,3.5924803199999995,{"$nulls":5},"zpracovat PD a realizace"]
[230,null,"Smíšená steka Staměřice - průtah obcí","Dolní Újezd","Staměřice","C9","ano","ano","ano",{"$nulls":4},0.29,2.1348756,{"$nulls":5},"zpracovat PD a realizace"]
[231,null,"Stezka pro cyklisty Staměřice- Skoky","Dolní Újezd","Staměřice, Skoky u Staměřic","C8","ano","ano","ano",{"$nulls":4},1.02,6.0070982399999995,{"$nulls":5},"zpracovat PD a realizace"]
[232,null,"Smíšená steka Skoky - průtah obcí","Dolní Újezd","Skoky u Staměřic","C9","ano","ano","ano",{"$nulls":4},0.56,4.122518400000001,{"$nulls":5},"zpracovat PD a realizace"]
[233,null,"Cyklistická komunikace Dolní Újezd  - Lipník nad Bečvou","Dolní Újezd","Dolní Újezd","B11",null,null,null,"ano",null,null,null,1.35,11.925856800000002,{"$nulls":5},"zpracovat PD a realizace"]
[234,null,"Cyklistická komunikace Dolní Újezd  - Lipník nad Bečvou","Dolní Újezd","Dolní Újezd","C9","ano","ano","ano",{"$nulls":4},0.38,2.23793856,{"$nulls":5},"zpracovat PD a realizace"]
[235,null,"Cyklistická komunikace Dolní Újezd  - Lipník nad Bečvou","Lipník nad Bečvou","Trnávka u Lipníka nad Bečvou","C9","ano","ano","ano",{"$nulls":4},0.18,1.0600761600000002,{"$nulls":5},"zpracovat PD a realizace"]
[236,null,"Cyklistická komunikace Dolní Újezd  - Lipník nad Bečvou","Lipník nad Bečvou","Trnávka u Lipníka nad Bečvou","B11",null,null,null,"ano",null,null,null,0.33,2.91520944,{"$nulls":5},"zpracovat PD a realizace"]
[237,null,"Cyklistická komunikace Dolní Újezd  - Lipník nad Bečvou","Osek nad Bečvou","Osek nad Bečvou","B11",null,null,null,"ano",null,null,null,0.078,0.689049504,{"$nulls":5},"zpracovat PD a realizace"]
[238,null,"Cyklistická komunikace Dolní Újezd  - Lipník nad Bečvou","Lipník nad Bečvou","Lipník nad Bečvou","C9","ano","ano","ano",{"$nulls":4},0.25,1.472328,{"$nulls":5},"zpracovat PD a realizace"]
[239,null,"Cyklistická komunikace Dolní Újezd  - Lipník nad Bečvou","Osek nad Bečvou","Osek nad Bečvou","C9","ano","ano","ano",{"$nulls":4},0.14,0.8245036800000001,{"$nulls":5},"zpracovat PD a realizace"]
[240,null,"Cyklistická komunikace Dolní Újezd  - Lipník nad Bečvou","Lipník nad Bečvou","Lipník nad Bečvou","B11",null,null,null,"ano",null,null,null,0.73,6.448796639999999,{"$nulls":5},"zpracovat PD a realizace"]
[241,null,"Vyhrazené jízdní pruhy Lipník nad Bečvou, ul. Osecká, Tyršova","Lipník nad Bečvou","Lipník nad Bečvou","V14+IP20","ano","ano","ano",{"$nulls":4},1.24,2.2506,{"$nulls":5},"zpracovat PD a realizace"]
[242,null,"Převedení cyklistů na křižovatce Na Horecku, Tyršova, Osecká","Lipník nad Bečvou","Lipník nad Bečvou","C10","ano","ano","ano",{"$nulls":4},0.085,0.8343192000000001]
[243,"B15","Cyklistická komunikace Prosenice - Lýsky","Prosenice","Prosenice","B11",null,null,null,"ano",null,null,null,1,8.833968,{"$nulls":5},"zpracovat PD a realizace"]
[244,null,"Cyklistická komunikace Osek nad Bečvou - Proseničky","Prosenice","Proseničky","B11",null,null,null,"ano",null,null,null,1.31,11.572498079999999,{"$nulls":5},"zpracovat PD a realizace"]
[245,null,"Cyklistická komunikace Osek nad Bečvou - Proseničky","Osek nad Bečvou","Osek nad Bečvou","B11",null,null,null,"ano",null,null,null,0.87,7.685552159999999,{"$nulls":5},"zpracovat PD a realizace"]
[246,null,"Vyhrazené jízdní pruhy Osek nad Bečvou","Osek nad Bečvou","Osek nad Bečvou","V14+IP20","ano","ano","ano",{"$nulls":4},1.65,2.9947499999999994,{"$nulls":5},"zpracovat PD a realizace"]
[247,null,"Přednádražní prostor - parkovací boxy","Osek nad Bečvou","Osek nad Bečvou","Stojany","ano",{"$nulls":5},"ano",null,1,null,null,"zpracování DSP, vydání SP","realizace"]
[248,null,"Smíšená stezka Lipník nad Bečvou - podél Bečvy","Lipník nad Bečvou","Lipník nad Bečvou","C9","ano","ano","ano",{"$nulls":4},1.62,9.540685439999999,{"$nulls":5},"zpracovat PD a realizace"]
[249,null,"Chodník pro chodce a cyklisty Lipník nad Bečvou, ul. Piaritrická","Lipník nad Bečvou","Lipník nad Bečvou","C10","ano","ano","ano",{"$nulls":4},0.15,1.472328,{"$nulls":5},"zpracovat PD a realizace"]
[250,null,"Vyhrazené jízdní pruhy Lipník nad Bečvou, ul. Hranická","Lipník nad Bečvou","Lipník nad Bečvou","V14+IP20","ano","ano","ano",{"$nulls":4},1.1,1.9965000000000002,{"$nulls":5},"zpracovat PD a realizace"]
[251,null,"Smíšená stezka Lipník - Jezernice","Lipník nad Bečvou","Lipník nad Bečvou","C9","ano","ano","ano",{"$nulls":4},0.54,3.18022848,{"$nulls":5},"zpracovat PD a realizace"]
[252,null,"Smíšená stezka Lipník - Jezernice","Jezernice","Jezernice","C9","ano","ano","ano",{"$nulls":4},1.19,7.008281279999999,{"$nulls":5},"zpracovat PD a realizace"]
[253,null,"Cyklistická komunikace Jezernice podél viaduktů","Jezernice","Jezernice","B11",{"$nulls":7},0.27,2.38517136,{"$nulls":5},"zpracovat PD a realizace"]
[254,null,"Smíšená stezka Jezernice - Slavíč","Jezernice","Jezernice","C9","ano","ano","ano",{"$nulls":4},0.93,5.47706016,{"$nulls":5},"zpracovat PD a realizace"]
[255,null,"Smíšená stezka Jezernice - Slavíč","Hranice","Slavíč","C9","ano","ano","ano",{"$nulls":4},0.67,3.94583904,{"$nulls":5},"zpracovat PD a realizace"]
[256,null,"Smíšená stezka Slavíč podél dráhy","Hranice","Slavíč","C9","ano","ano","ano",{"$nulls":4},0.69,4.063625279999999,{"$nulls":5},"zpracovat PD a realizace"]
[257,null,"Cyklistická komunikace Slavíč - Drahotuše","Hranice","Slavíč","B11",null,null,null,"ano",null,null,null,0.28,2.4735110400000004,{"$nulls":5},"zpracovat PD a realizace"]
[258,null,"Cyklistická komunikace Slavíč - Drahotuše","Hranice","Slavíč","C9","ano","ano","ano",{"$nulls":4},0.2,1.1778624,{"$nulls":5},"zpracovat PD a realizace"]
[259,null,"Cyklistická komunikace Slavíč - Drahotuše","Klokočí","Klokočí","C9","ano","ano","ano",{"$nulls":4},0.54,3.18022848,{"$nulls":5},"zpracovat PD a realizace"]
[260,null,"Cyklistická komunikace Slavíč - Drahotuše","Hranice","Drahotuše","C9","ano","ano","ano",{"$nulls":4},0.57,3.3569078399999994,{"$nulls":5},"zpracovat PD a realizace"]
[261,null,"Cyklistická komunikace Slavíč - Drahotuše","Hranice","Drahotuše","B11",null,null,null,"ano",null,null,null,0.4,3.5335872000000004,{"$nulls":5},"zpracovat PD a realizace"]
[262,null,"Vyhrazené jízdní pruhy Drahotuše, ul. Hranická, Lipnická","Hranice","Drahotuše","V14+IP20","ano","ano","ano",{"$nulls":4},1.52,11.189692800000003,{"$nulls":5},"zpracovat PD a realizace"]
[263,null,"Cyklistická komunikace Drahotuše (východ na Hranice)","Hranice","Drahotuše","B11",{"$nulls":7},0.6,5.300380799999999,{"$nulls":5},"zpracovat PD a realizace"]
[264,null,"Smíšená stezka Drahotuše - Hranice","Hranice","Hranice","C9",{"$nulls":7},0.29,1.7079004799999995,{"$nulls":5},"zpracovat PD a realizace"]
[265,"B16","Stezka pro cyklisty Přerov - Bochoř v trase opuštěné II/436","Bochoř","Bochoř","C8","ano","ano","ano",{"$nulls":4},1.55,0.1,{"$nulls":5},"zpracovat PD a realizace"]
[266,null,"Cyklistická komunikace Bochoř (západ, za humny k dráze)","Bochoř","Bochoř","B11",null,null,null,"ano",null,null,null,0.7,6.183777599999998,{"$nulls":5},"zpracovat PD a realizace"]
[267,null,"Cyklistická komunikace Bochoř - Horní Moštěnice, zastávka","Bochoř","Bochoř","B11",null,null,null,"ano",null,null,null,0.56,4.947022080000001,{"$nulls":5},"zpracovat PD a realizace"]
[268,null,"Cyklistická komunikace Bochoř - Horní Moštěnice, zastávka","Horní Moštěnice","Horní Moštěnice","B11",null,null,null,"ano",null,null,null,1.17,10.335742559999998,{"$nulls":5},"zpracovat PD a realizace"]
[269,null,"Smíšená stezka Bochoř - Vlkoš","Bochoř","Bochoř","C9","ano","ano","ano",{"$nulls":4},1.92,11.307479039999999,{"$nulls":5},"zpracovat PD a realizace"]
[270,null,"Smíšená stezka Bochoř - Vlkoš  - Chropyně (hranice kraje)","Vlkoš","Vlkoš u Přerova","C9","ano","ano","ano",{"$nulls":4},3.97,23.380568639999996,{"$nulls":5},"zpracovat PD a realizace"]
[271,null,"Smíšená stezka Chropyně (hranice kraje) - Kojetín","Kojetín ","Kojetín ","C9","ano","ano","ano",{"$nulls":4},2.95,17.373470400000002,{"$nulls":5},"zpracovat PD a realizace"]
[272,null,"Vyhrazené jízdní pruhy Kojetín, ul. Kroměřížská","Kojetín ","Kojetín ","V14+IP20","ano","ano","ano",{"$nulls":4},0.73,1.32495,{"$nulls":5},"zpracovat PD a realizace"]
[273,null,"Vyhrazené jízdní pruhy Kojetín, ul. Kroměřížská","Kojetín ","Kojetín ","V14+IP20","ano","ano","ano",{"$nulls":4},0.35,0.6352499999999999,{"$nulls":5},"zpracovat PD a realizace"]
[274,null,"Smíšená stezka Kojetín - Měrovice (podél dráhy)","Kojetín ","Kojetín ","C9","ano","ano","ano",{"$nulls":4},2.49,14.66438688,{"$nulls":5},"zpracovat PD a realizace"]
[275,null,"Smíšená stezka Kojetín - Měrovice (podél dráhy)","Měrovice nad Hanou","Měrovice nad Hanou","C9","ano","ano","ano",{"$nulls":4},1.24,7.302746879999999,{"$nulls":5},"zpracovat PD a realizace"]
[276,null,"Smíšená stezka Měrovice - u křížení s dráhou","Měrovice nad Hanou","Měrovice nad Hanou","C9","ano","ano","ano",{"$nulls":4},0.15,1.1042459999999998,{"$nulls":5},"zpracovat PD a realizace"]
[277,null,"Smíšená stezka Měrovice - Hruška","Měrovice nad Hanou","Měrovice nad Hanou","C9","ano","ano","ano",{"$nulls":4},0.824,4.852793087999999,{"$nulls":5},"zpracovat PD a realizace"]
[278,null,"Smíšená stezka Měrovice - Hruška","Hruška","Hruška","C9","ano","ano","ano",{"$nulls":4},1.497,8.816300064000002,{"$nulls":5},"zpracovat PD a realizace"]
[279,null,"Smíšená stezka Hruška, za humny","Hruška","Hruška","C9","ano","ano","ano",{"$nulls":4},0.22,1.2956486399999998,{"$nulls":5},"zpracovat PD a realizace"]
[280,null,"Smíšená stezka Hruška - Tvorovice","Hruška","Hruška","C9","ano","ano","ano",{"$nulls":4},0.6,3.5335871999999995,{"$nulls":5},"zpracovat PD a realizace"]
[281,null,"Smíšená stezka Hruška - Tvorovice","Tvorovice","Tvorovice","C9","ano","ano","ano",{"$nulls":4},0.53,3.1213353600000002,{"$nulls":5},"zpracovat PD a realizace"]
[282,null,"Cyklistická komunikace Tvorovice - Obětkovice","Tvorovice","Tvorovice","C9","ano","ano","ano",{"$nulls":4},0.46,2.70908352,{"$nulls":5},"zpracovat PD a realizace"]
[283,null,"Cyklistická komunikace Tvorovice - Obětkovice - Klenovice","Obědkovice","Obědkovice","B11",null,null,null,"ano",null,null,null,1.93,17.04955824,{"$nulls":5},"zpracovat PD a realizace"]
[284,null,"Cyklistická komunikace Tvorovice - Klenovice (U Větrníku)","Klenovice na Hané","Klenovice na Hané","B11",null,null,null,"ano",null,null,null,0.58,5.123701439999999,{"$nulls":5},"zpracovat PD a realizace"]
[285,null,"Cyklistická komunikace Klenovice (U Větrníku) - Čelčice","Klenovice na Hané","Klenovice na Hané","B11",null,null,null,"ano",null,null,null,1.195,10.55659176,{"$nulls":5},"zpracovat PD a realizace"]
[286,null,"Cyklistická komunikace Klenovice (U Větrníku) - Čelčice (podél dráhy)","Čelčice na Hané","Čelčice na Hané","B11",null,null,null,"ano",null,null,null,0.57,5.03536176,{"$nulls":5},"zpracovat PD a realizace"]
[287,null,"Smíšená stezka Čelčice na Hané podél dráhy (napojení na stávající stezku)","Čelčice na Hané","Čelčice na Hané","C9","ano","ano","ano",{"$nulls":4},0.25,1.472328,{"$nulls":5},"zpracovat PD a realizace"]
[288,"B16a","Smíšená stezka Měrovice n. H. - Němčice n. H.","Hruška","Hruška","C9","ano","ano","ano",{"$nulls":4},0.422,2.4852896639999997,{"$nulls":5},"zpracovat PD a realizace"]
[289,null,"Smíšená stezka Měrovice n. H. - Němčice n. H.","Němčice nad Hanou","Němčice nad Hanou","C9","ano","ano","ano",{"$nulls":4},0.68,4.00473216,{"$nulls":5},"zpracovat PD a realizace"]
[290,null,"Smíšená stezka Němčice n. H. - Víceměřice","Němčice nad Hanou","Němčice nad Hanou","C9","ano","ano","ano",{"$nulls":4},1.34,7.89167808,{"$nulls":5},"zpracovat PD a realizace"]
[291,null,"Smíšená stezka Němčice n. H. - Víceměřice","Víceměřice","Víceměřice","C9","ano","ano","ano",{"$nulls":4},0.43,2.53240416,{"$nulls":5},"zpracovat PD a realizace"]
[292,null,"Smíšená stezka Víceměřice - Doloplazy, vpravo podél dráhy","Víceměřice","Víceměřice","C9","ano","ano","ano",{"$nulls":4},0.58,3.415800959999999,{"$nulls":5},"zpracovat PD a realizace"]
[293,null,"Smíšená stezka Víceměřice - Doloplazy, vpravo podél dráhy","Doloplazy","Doloplazy","C9","ano","ano","ano",{"$nulls":4},0.11,0.6478243199999999,{"$nulls":5},"zpracovat PD a realizace"]
[294,null,"Podjezd pod dráhou - Doloplazy","Doloplazy","Doloplazy","B11",{"$nulls":7},0.025,0.22084920000000002,{"$nulls":5},"zpracovat PD a realizace"]
[295,null,"Smíšená stezka Doloplazy, vlevo podél dráhy","Doloplazy","Doloplazy","C9","ano","ano","ano",{"$nulls":4},0.38,2.23793856,{"$nulls":5},"zpracovat PD a realizace"]
[296,null,"Cyklistická komunikace Doloplazy - Pivín","Doloplazy","Doloplazy","B11",null,null,null,"ano",null,null,null,0.26,2.2968316800000004,{"$nulls":5},"zpracovat PD a realizace"]
[297,null,"Cyklistická komunikace Doloplazy - Pivín","Dobromilice","Dobromilice","B11",null,null,null,"ano",null,null,null,0.12,1.06007616,{"$nulls":5},"zpracovat PD a realizace"]
[298,null,"Cyklistická komunikace Doloplazy - Pivín","Dobromilice","Dobromilice","C9","ano","ano","ano",{"$nulls":4},2.23,13.133165759999999,{"$nulls":5},"zpracovat PD a realizace"]
[299,null,"Cyklistická komunikace Doloplazy - Pivín","Pivín","Pivín","C9","ano","ano","ano",{"$nulls":4},2.04,12.014196479999999,{"$nulls":5},"zpracovat PD a realizace"]
[300,null,"Cyklistická komunikace Doloplazy - Pivín","Pivín","Pivín","B11",{"$nulls":7},0.17,1.50177456,{"$nulls":5},"zpracovat PD a realizace"]
[301,null,"Smíšená stezka Pivín - Klenovice na Hané","Pivín","Pivín","C9","ano","ano","ano",{"$nulls":4},0.68,4.00473216,{"$nulls":5},"zpracovat PD a realizace"]
[302,null,"Smíšená stezka Pivín - Klenovice na Hané","Klenovice na Hané","Klenovice na Hané","C9","ano","ano","ano",{"$nulls":4},0.83,4.8881289599999995,{"$nulls":5},"zpracovat PD a realizace"]
[303,"B17","Smíšená stezka Hněvotín - Lutín (od silnice III/5709)","Hněvotín","Hněvotín","C9","ano","ano","ano",{"$nulls":4},1.07,6.301563839999999,{"$nulls":5},"zpracovat PD a realizace"]
[304,null,"Smíšená stezka Hněvotín - Lutín (ke hřišti)","Lutín","Lutín","C9","ano","ano","ano",{"$nulls":4},0.45,2.6501904,{"$nulls":5},"zpracovat PD a realizace"]
[305,null,"Smíšená stezka Olšany - Lutín (podél III/57011)","Lutín","Lutín","C9","ano","ano","ano",null,null,null,"ano",0.219,1.289759328,null,null,"zpracování DUR, vydání ÚR","zpracování DSP, vydání SP","realizace"]
[306,null,"Smíšená stezka Olšany - Lutín (podél III/57011)","Hněvotín","Hněvotín","C9","ano","ano","ano",null,null,null,"ano",0.752,4.428762624,null,null,"zpracování DUR, vydání ÚR","zpracování DSP, vydání SP","realizace"]
[307,null,"Smíšená stezka Olšany - Lutín (podél III/57011)","Olšany u Prostějova","Olšany u Prostějova","C9","ano","ano","ano",null,null,null,"ano",1.61,9.481792319999998,null,null,"zpracování DUR, vydání ÚR","zpracování DSP, vydání SP","realizace"]
[308,"B18","Vyhrazené jízdní pruhy na průtahu silnice II/448","Ústín","Ústín","V14+IP20","ano","ano","ano",null,null,null,"ano",0.625,4.601025000000001,null,"iniciovat jednání s Ol. Krajem","zpracování DSP, vydání SP","realizace",null,null,"realizace nutné zkoordinovat s rekonstrukcí II/448"]
[309,"C1","Smíšená stezka Žešov - Výšovice","Výšovice","Výšovice","C9","ano","ano","ano",{"$nulls":4},1.19,7.008281279999999,{"$nulls":5},"zpracovat PD a realizace"]
[310,"C2","Smíšená stezka Prostějov - Určice","Určice","Určice","C9","ano","ano","ano",{"$nulls":4},2.04,12.014196479999999,{"$nulls":5},"zpracovat PD a realizace"]
[311,"C3","Vyhrazené jízdní pruhy na II/377 v Mostkovicích, ul. Prostějovská","Mostkovice","Mostkovice","V14+IP20","ano","ano","ano",{"$nulls":4},0.508,0.92202,{"$nulls":5},"zpracovat PD a realizace"]
[312,null,"Smíšená stezka Domamyslice - Mostkovice","Mostkovice","Mostkovice","C9","ano","ano","ano",{"$nulls":4},0.514,3.0271063679999997,{"$nulls":5},"zpracovat PD a realizace"]
[313,null,"Cyklistická komunikace Mostkovice (ul. Pod Lesem) - hráz Plumlovské přehrady","Mostkovice","Mostkovice","B11",null,null,null,"ano",null,null,null,0.838,7.4028651839999995,{"$nulls":5},"zpracovat PD a realizace"]
[314,null,"Smíšená stezka podél severního břehu Plumlovské přehrady","Mostkovice","Stichovice","C9","ano","ano","ano",{"$nulls":4},0.431,2.538293472,{"$nulls":5},"zpracovat PD a realizace"]
[315,null,"Smíšená stezka podél severního břehu Plumlovské přehrady","Plumlov","Plumlov","C9","ano","ano","ano",{"$nulls":4},1.314,7.738555968,{"$nulls":5},"zpracovat PD a realizace"]
[316,"C4","Cyklistická komunikace Luká - Vilémov","Luká","Luká","C9","ano","ano","ano",{"$nulls":4},1.08,6.36045696,{"$nulls":5},"zpracovat PD a realizace"]
[317,null,"Cyklistická komunikace Luká - Vilémov","Vilémov","Vilémov u Litovle","C9","ano","ano","ano",{"$nulls":4},1.84,10.83633408,{"$nulls":5},"zpracovat PD a realizace"]
[318,null,"Cyklistická komunikace Luká - Vilémov","Vilémov","Vilémov u Litovle","B11",null,null,null,"ano",null,null,null,0.18,1.5901142400000001,{"$nulls":5},"zpracovat PD a realizace"]
[319,null,"Cyklistická komunikace Cakov - Nové Dvory - Náměšť na Hané","Senice na Hané","Cakov","B11",null,null,null,"ano",null,null,null,0.69,6.095437919999999,{"$nulls":5},"zpracovat PD a realizace"]
[320,null,"Cyklistická komunikace Cakov - Nové Dvory - Náměšť na Hané","Náměšť na Hané","Náměšť na Hané","C9","ano","ano","ano",{"$nulls":4},1.51,8.89286112,{"$nulls":5},"zpracovat PD a realizace"]
[321,null,"Cyklistická komunikace Cakov - Nové Dvory - Náměšť na Hané","Náměšť na Hané","Náměšť na Hané","B11",null,null,null,"ano",null,null,null,0.84,7.42053312,{"$nulls":5},"zpracovat PD a realizace"]
[322,null,"Chodník s povolením cyklistů Loučany na křížení s II/449","Loučany","Loučany na Hané","C7+E13","ano","ano","ano",{"$nulls":4},0.063,0.30918888000000005,{"$nulls":5},"zpracovat PD a realizace"]
[323,null,"Cyklistická komunikace Loučany podél družstva","Loučany","Loučany na Hané","B11",{"$nulls":7},0.47,4.151964959999999,{"$nulls":5},"zpracovat PD a realizace"]
[324,null,"Cyklistická komunikace Tešetice směr Loučany ","Tešetice","Těšetice","B11",null,null,null,"ano",null,null,null,0.89,7.862231519999999,{"$nulls":5},"zpracovat PD a realizace"]
[325,"C5","Cyklistická komunikace Senice na Hané - Příkazy","Senice na Hané","Senice na Hané","B11",null,null,null,"ano",null,null,null,0.466,4.116629088000001,null,null,"zpracování DUR","zpracování DSP","realizace"]
[326,null,"Cyklistická komunikace Senice na Hané - Příkazy","Senice na Hané","Senice na Hané","C9","ano","ano","ano",{"$nulls":4},1.417,8.345155104,null,null,"zpracování DUR","zpracování DSP","realizace"]
[327,null,"Cyklistická komunikace Senice na Hané - Příkazy","Příkazy","Příkazy","C9","ano","ano","ano",{"$nulls":4},0.82,4.829235839999999,null,null,"zpracování DUR","zpracování DSP","realizace"]
[328,null,"Cyklistická komunikace Senice na Hané - Příkazy","Příkazy","Příkazy","B11",null,null,null,"ano",null,null,null,0.733,6.475298543999999,null,null,"zpracování DUR","zpracování DSP","realizace"]
[329,"C6","Smíšená stezka Březecká (křížení III/44613)","Štěpánov","Štěpánov u Olomouce","C9","ano","ano","ano",{"$nulls":4},0.291,2.14223724,null,null,"zpracování DUR / DSP","realizace"]
[330,null,"Cyklistická komunikace Březecká, po ul. Dolní","Štěpánov","Štěpánov u Olomouce","B11",{"$nulls":7},0.61,5.38872048,null,null,"zpracování DUR / DSP","realizace"]
[331,null,"Chodník s povolením cyklistů Štěpánov - k nádraží","Štěpánov","Štěpánov u Olomouce","C7+E13","ano","ano","ano",{"$nulls":4},0.15,0.736164,null,null,"zpracování DUR / DSP","realizace"]
[332,null,"Přednádražní prostor - parkovací boxy","Štěpánov","Štěpánov u Olomouce","Stojany","ano","ano",{"$nulls":6},1,null,null,"zpracování DSP, vydání SP","realizace"]
[333,null,"Vyhrazené jízdní pruhy na průtahu silnice II/44613, ul. Dolní, Horní","Štěpánov","Štěpánov u Olomouce","V14+IP20","ano","ano","ano",null,null,null,"ano",1.6,2.9040000000000004,null,"iniciovat jednání s Ol. Krajem","zpracování DSP, vydání SP","realizace"]
[334,"C7","Smíšená stezka Uničov - Troubelice","Uničov","Uničov, Nová Dědina u Uničova","C9","ano","ano","ano",{"$nulls":4},2.07,12.190875839999997,{"$nulls":5},"zpracovat PD a realizace"]
[335,"C8","Smíšená stezka Nová Dědina - Tekro - hranice katastru","Uničov","Nová Dědina u Uničova","C9","ano","ano","ano",null,null,"ano",null,0.94,5.535953279999998,null,"do konce roku DSP","vydání SP","realizace"]
[336,"C9","Smíšená stezka Uničov - Dolní Sukolom","Uničov","Uničov, Dolní Sukolom","C9","ano","ano","ano",{"$nulls":4},0.87,5.123701439999999,{"$nulls":5},"zpracovat PD a realizace"]
[337,null,"Smíšená stezka Dolní Sukolom - intravilán","Uničov","Dolní Sukolom  ","C9","ano","ano","ano",{"$nulls":4},0.4,2.9446560000000006,{"$nulls":5},"zpracovat PD a realizace"]
[338,null,"Smíšená stezka Dolní Sukolom - Horní Sukolom","Uničov","Dolní Sukolom, Horní Sukolom","C9","ano","ano","ano",{"$nulls":4},0.87,5.123701439999999,{"$nulls":5},"zpracovat PD a realizace"]
[339,null,"Smíšená stezka Horní Sukolom  - intravilán","Uničov","Horní Sukolom  ","C9","ano","ano","ano",{"$nulls":4},0.44,3.2391216000000003,{"$nulls":5},"zpracovat PD a realizace"]
[340,null,"Smíšená stezka Horní Sukolom - Dlouhá Loučka, hranice k.ú.","Uničov","Horní Sukolom  ","C9","ano","ano","ano",{"$nulls":4},1.06,6.2426707200000005,{"$nulls":5},"zpracovat PD a realizace"]
[341,"C10","Cyklostezka Dolní Žleb","Šternberk","Šternberk","C9","ano","ano","ano",null,null,"ano",null,0.964,7.09662096,null,"dokončování DUR","zpracování a vydání SP","realizace",null,null,"dle akčního plánu města Šternberka"]
[342,"C11","Cyklistická komunikace Šternberk - Domašov u Šternberka","Šternberk","Šternberk, Lhota u Šternberka","B11",null,null,null,"ano",null,null,null,1.75,15.459444,{"$nulls":5},"zpracovat PD a realizace"]
[343,null,"Cyklistická komunikace Šternberk - Domašov u Šternberka","Domašov u Šternberka","Domašov u Šternberka","B11",null,null,null,"ano",null,null,null,0.075,0.6625475999999999,{"$nulls":5},"zpracovat PD a realizace"]
[344,null,"Smíšená steka Domašov u Šternberka","Domašov u Šternberka","Domašov u Šternberka","C9","ano","ano","ano",{"$nulls":4},0.257,1.8919414800000003,{"$nulls":5},"zpracovat PD a realizace"]
[345,null,"Smíšená steka Hraničné Petrovice na spojnici III/44441 a II/444","Hraničné Petrovice","Hraničné Petrovice","C9","ano","ano","ano",{"$nulls":4},0.17,1.00118304,{"$nulls":5},"zpracovat PD a realizace"]
[346,"C12","Cyklistická komunikace Hrubá Voda","Hlubočky","Hrubá Voda","B11",{"$nulls":4},"ano",null,null,2.72,24.02839296,{"$nulls":5},"zpracovat PD a realizace"]
[347,null,"Cyklostezka Domašov- Jívová","Jívová","Jívová","B11",{"$nulls":4},"ano",null,null,1.26,11.13079968,{"$nulls":5},"zpracovat PD a realizace"]
[348,null,"Cyklostezka Domašov- Jívová","Domašov nad Bystřicí","Domašov nad Bystřicí","B11",{"$nulls":4},"ano",null,null,0.5,4.416984,{"$nulls":5},"zpracovat PD a realizace"]
[349,null,"Přednádražní prostor - parkovací boxy","Jívová","Jívová","Stojany",{"$nulls":6},"ano",null,1,null,null,"zpracování DSP, vydání SP","realizace"]
[350,null,"Cyklistická komunikace Domašov nad Bystřicí","Domašov nad Bystřicí","Domašov nad Bystřicí","B11",{"$nulls":4},"ano",null,null,3.75,33.127379999999995,{"$nulls":5},"zpracovat PD a realizace"]
[351,"C13","Stezka pro chodce a cyklisty Dolany - Bělkovice-Lašťany ","Bělkovice-Lašťany","Bělkovice","C9","ano","ano","ano",null,null,"ano",null,1.13,6.654922559999999,null,"zadána aktualizace DSP z roku 2009","realizace"]
[352,null,"Stezka pro chodce a cyklisty Dolany - Bělkovice-Lašťany ","Dolany","Dolany u Olomouce","C9","ano","ano","ano",null,null,"ano",null,0.638,3.757381056,null,"zadána aktualizace DSP z roku 2009","realizace"]
[353,null,"Stezka pro chodce a cyklisty Dolany - Bělkovice-Lašťany ","Dolany","Dolany u Olomouce","B11",{"$nulls":7},0.11,0.97173648,null,"zadána aktualizace DSP z roku 2009","realizace"]
[354,null,"Cyklistická komunikace Dolany (hřbitov) - Tovéř","Toveř","Toveř","B11",{"$nulls":5},"ano",null,0.54,4.77034272,{"$nulls":5},"zpracovat PD a realizace"]
[355,null,"Cyklistická komunikace Toveř - Chválkovice (západ)","Toveř","Toveř","C9","ano","ano","ano",{"$nulls":4},0.463,2.726751456,{"$nulls":5},"zpracovat PD a realizace"]
[356,null,"Cyklistická komunikace Toveř - Chválkovice (západ)","Samotišky","Samotišky","C9","ano","ano","ano",{"$nulls":4},0.72,4.240304640000001,{"$nulls":5},"zpracovat PD a realizace"]
[357,null,"Cyklistická komunikace Toveř - Chválkovická stezka (západ)","Samotišky","Samotišky","B11",{"$nulls":5},"ano",null,1.11,9.805704480000001,{"$nulls":5},"zpracovat PD a realizace"]
[358,null,"Cyklistická komunikace Chválkovice - Droždín","Olomouc","Droždín","B11",{"$nulls":5},"ano",null,0.86,7.5972124800000005,{"$nulls":5},"zpracovat PD a realizace"]
[359,null,"Smíšená stezka Toveř - Samotišky (východ)","Toveř","Toveř","C9","ano","ano","ano",{"$nulls":4},0.6,3.5335871999999995,{"$nulls":5},"zpracovat PD a realizace"]
[360,null,"Smíšená stezka Toveř - Samotišky (východ)","Samotišky","Samotišky","C9","ano","ano","ano",{"$nulls":4},0.18,1.0600761600000002,{"$nulls":5},"zpracovat PD a realizace"]
[361,null,"Smíšená stezka Samotišky - Droždín podél III/4436","Samotišky","Samotišky","C9","ano","ano","ano",{"$nulls":4},0.216,1.2720913919999999,{"$nulls":5},"zpracovat PD a realizace"]
[362,null,"Smíšená stezka Samotišky - Droždín podél III/4436","Olomouc","Droždín","C9","ano","ano","ano",{"$nulls":4},0.723,4.257972576,{"$nulls":5},"zpracovat PD a realizace"]
[363,null,"Stezka pro chodce a cyklisty Droždín, ul. U cihelny","Olomouc","Droždín","C10","ano","ano","ano",{"$nulls":4},0.1,0.7852416,{"$nulls":5},"zpracovat PD a realizace"]
[364,null,"Smíšená stezka Droždín - Bystrovany podél III/4436","Olomouc","Droždín","C9","ano","ano","ano",{"$nulls":4},0.99,5.830418879999999,{"$nulls":5},"zpracovat PD a realizace"]
[365,null,"Smíšená stezka Droždín - Bystrovany podél III/4436","Bystrovany","Bystrovany","C9","ano","ano","ano",{"$nulls":4},0.62,3.6513734399999995,{"$nulls":5},"zpracovat PD a realizace"]
[366,null,"Propojení podél dráhy do ul. Droždínská","Bystrovany","Bystrovany","B11",{"$nulls":7},0.11,0.97173648,{"$nulls":5},"zpracovat PD a realizace"]
[367,"C14","Cyklistická komunikace Bělkovice - Lašťany za humny v trase 6029","Bělkovice-Lašťany","Bělkovice","B11",null,null,null,"ano",null,null,null,0.55,4.8586824,{"$nulls":5},"zpracovat PD a realizace"]
[368,null,"Smíšená stezka Bělkovice - Lašťany - propojka od Trusovického potoka po křižovatku III/44313 a III/44436","Bělkovice-Lašťany","Bělkovice","C9","ano","ano","ano",{"$nulls":4},0.12,0.7067174399999999,{"$nulls":5},"zpracovat PD a realizace"]
[369,"C16","Cyklistická komunikace Hranice - Bělotín","Hranice","Velká u Hranic","C9","ano","ano","ano",{"$nulls":4},0.16,0.9422899199999998,{"$nulls":5},"zpracovat PD a realizace"]
[370,null,"Cyklistická komunikace Hranice - Bělotín","Hranice","Velká u Hranic","C8","ano","ano","ano",{"$nulls":4},0.28,1.6490073600000001,{"$nulls":5},"zpracovat PD a realizace"]
[371,null,"Cyklistická komunikace Hranice - Bělotín","Hranice","Velká u Hranic","C9","ano","ano","ano",{"$nulls":4},0.744,4.381648128,{"$nulls":5},"zpracovat PD a realizace"]
[372,"C18","Smíšená stezka Přerov - Horní Moštěnice","Horní Moštěnice","Horní Moštěnice","C9","ano","ano","ano",{"$nulls":4},1.105,6.507689759999999,{"$nulls":5},"zpracovat PD a realizace"]
[373,"C19","Smíšená stezka Blatec-Kocanda - Charváty podél II/435","Blatec","Blatec","C9","ano","ano","ano",{"$nulls":4},0.48,2.8268697599999997,{"$nulls":5},"zpracovat PD a realizace"]
[374,null,"Smíšená stezka Blatec-Kocanda - Charváty podél II/435","Charváty","Charváty","C9","ano","ano","ano",{"$nulls":4},0.31,1.8256867199999998,{"$nulls":5},"zpracovat PD a realizace"]
[375,null,"Cyklistická komunikace Věrovany - Tovačov přes rybníky","Věrovany","Věrovany","B11",null,null,null,"ano",null,null,null,1.29,11.39581872,{"$nulls":5},"zpracovat PD a realizace"]
[376,null,"Cyklistická komunikace Věrovany - Tovačov přes rybníky","Tovačov","Tovačov","B11",null,null,null,"ano",null,null,null,3.38,29.85881184,{"$nulls":5},"zpracovat PD a realizace"]
[377,null,"Autobusové nádraží - parkovací boxy","Tovačov","Tovačov","Stojany",{"$nulls":6},"ano",null,1,null,null,"zpracování DSP, vydání SP","realizace"]
[378,null,"Smíšená stezka Tovačov - Annín podél Mlýnského náhonu","Tovačov","Tovačov","C9","ano","ano","ano",null,null,null,"ano",0.86,3.3765388799999996,null,null,"zpracování DUR / DSP","realizace"]
[379,null,"Cyklistická komunikace Annín","Tovačov","Tovačov","B11",{"$nulls":6},"ano",0.34,3.00354912,{"$nulls":5},"zpracovat PD a realizace"]
[380,null,"Smíšená steka Tovačov - Lobodice","Tovačov","Tovačov","C9","ano","ano","ano",null,null,null,"ano",0.5329999999999999,3.1390032959999994,{"$nulls":5},"zpracovat PD a realizace"]
[381,null,"Smíšená steka Tovačov - Lobodice","Oplocany","Oplocany","C9","ano","ano","ano",null,null,null,"ano",0.48,2.8268697599999997,{"$nulls":5},"zpracovat PD a realizace"]
[382,null,"Smíšená steka Tovačov - Lobodice","Lobodice","Lobodice","C9","ano","ano","ano",null,null,null,"ano",1.01,5.94820512,{"$nulls":5},"zpracovat PD a realizace"]
[383,null,"Cyklistická komunikace Lobodice - Uhřičice - Kojetín","Lobodice","Lobodice","B11",{"$nulls":6},"ano",0.26,2.2968316800000004,null,"aktualizuje se studie","zpracování DUR","zpracování DSP","realizace"]
[384,null,"Cyklistická komunikace Lobodice - Uhřičice - Kojetín","Lobodice","Lobodice","C9","ano","ano","ano",null,null,null,"ano",1.333,7.850452895999999,null,"aktualizuje se studie","zpracování DUR","zpracování DSP","realizace"]
[385,null,"Cyklistická komunikace Lobodice - Uhřičice - Kojetín","Uhřičice","Uhřičice","C9","ano","ano","ano",null,null,null,"ano",1.648,9.705586175999999,null,"aktualizuje se studie","zpracování DUR","zpracování DSP","realizace"]
[386,null,"Cyklistická komunikace Lobodice - Uhřičice - Kojetín","Kojetín","Kojetín","C9","ano","ano","ano",null,null,null,"ano",0.999,5.883422688,null,"aktualizuje se studie","zpracování DUR","zpracování DSP","realizace"]
[387,null,"Cyklistická komunikace Lobodice - Uhřičice - Kojetín","Kojetín","Kojetín","B11",{"$nulls":6},"ano",0.327,2.8887075360000005,null,"aktualizuje se studie","zpracování DUR","zpracování DSP","realizace"]
[388,null,"Vyhrazené jízdní pruhy Kojetín, ul. Olomoucká","Kojetín","Kojetín","V14+IP20","ano","ano","ano",null,null,null,"ano",0.645,1.170675,null,null,"zpracování DSP","realizace"]
[389,"C20","Smíšená stezka Nedvězí - Hněvotín - Topolany","Hněvotín","Hněvotín","C9","ano","ano","ano",null,null,null,"ano",0.994,5.853976128,null,"zpracovává se studie","zpracování DUR","zpracování DSP","realizace"]
[390,"C21","Smíšená stezka Luběnice - Lutín","Luběnice","Luběnice","C9","ano","ano","ano",{"$nulls":4},0.6,3.5335871999999995,{"$nulls":5},"zpracovat PD a realizace"]
[391,null,"Smíšená stezka Luběnice - Lutín","Lutín","Lutín","C9","ano","ano","ano",{"$nulls":4},1.19,7.008281279999999,{"$nulls":5},"zpracovat PD a realizace"]
[392,null,"Cyklistická komunikace Lutín za humny","Lutín","Lutín","B11",{"$nulls":7},0.27,2.38517136,{"$nulls":5},"zpracovat PD a realizace"]
[393,null,"Smíšená stezka Lutín - centrum","Lutín","Lutín","C9","ano","ano","ano",{"$nulls":4},0.27,1.9876428000000004,{"$nulls":5},"zpracovat PD a realizace"]
[394,null,"Stezka pro chodce a cyklisty Lutín - autobusové nádraží","Lutín","Lutín","C10","ano","ano","ano",{"$nulls":4},0.655,6.4291656,{"$nulls":5},"zpracovat PD a realizace"]
[395,"C22","Smíšená stezka Drahanovice - Rataje","Drahanovice","Drahanovice","C9","ano","ano","ano",{"$nulls":4},0.53,3.1213353600000002,{"$nulls":5},"zpracovat PD a realizace"]
[396,null,"Smíšená stezka Drahanovice - Rataje","Tešetice","Rataje u Olomouce","C9","ano","ano","ano",{"$nulls":4},1.4,8.245036799999998,{"$nulls":5},"zpracovat PD a realizace"]
[397,"C23","Smíšená stezka Jesenec - Konice","Jesenec","Jesenec","C9","ano","ano","ano",{"$nulls":4},0.97,5.71263264,{"$nulls":5},"zpracovat PD a realizace"]
[398,null,"Smíšená stezka Jesenec - Konice","Konice","Konice","C9","ano","ano","ano",{"$nulls":4},1.13,6.654922559999999,{"$nulls":5},"zpracovat PD a realizace"]
[399,"C24","Cyklistická komunikace Mladeč - Pateřín","Bílá Lhota","Bílá Lhota, Pateřín","B11",null,null,null,"ano",null,null,null,1.81,15.98948208,{"$nulls":5},"zpracovat PD a realizace"]
[400,null,"Cyklistická komunikace Mladeč - Pateřín","Bílá Lhota","Pateřín, Měník","C9","ano","ano","ano",{"$nulls":4},1.94,11.42526528,{"$nulls":5},"zpracovat PD a realizace"]
[401,null,"Cyklistická komunikace Mladeč - Pateřín","Bílá Lhota","Měník","B11",null,null,null,"ano",null,null,null,0.52,4.593663360000001,{"$nulls":5},"zpracovat PD a realizace"]
[402,null,"Cyklistická komunikace Mladeč - Pateřín","Mladeč","Mladeč","B11",null,null,null,"ano",null,null,null,1.07,9.45234576,{"$nulls":5},"zpracovat PD a realizace"]
[403,"C25","Cyklistická komunikace Hradečná - Slavětín","Bílá Lhota","Hradečná u Bílé Lhoty","B11",null,null,null,"ano",null,null,null,0.09,0.7950571200000001,{"$nulls":5},"zpracovat PD a realizace"]
[404,null,"Cyklistická komunikace Hradečná - Slavětín","Slavětín","Slavětín u Litovle","B11",null,null,null,"ano",null,null,null,1.69,14.92940592,{"$nulls":5},"zpracovat PD a realizace"]
[405,"C26","Cyklistická komunikace Hradečná - Měrotín","Bílá Lhota","Hradečná u Bílé Lhoty","B11",null,null,null,"ano",null,null,null,0.52,4.593663360000001,{"$nulls":5},"zpracovat PD a realizace"]
[406,null,"Cyklistická komunikace Hradečná - Měrotín","Měrotín","Měrotín","B11",null,null,null,"ano",null,null,null,0.3,2.6501903999999996,{"$nulls":5},"zpracovat PD a realizace"]
[407,null,"Cyklistická komunikace Měrotín - Chodubín","Měrotín","Měrotín","B11",null,null,null,"ano",null,null,null,0.19,1.6784539200000002,{"$nulls":5},"zpracovat PD a realizace"]
[408,null,"Cyklistická komunikace Měrotín - Chodubín","Litovel","Chudobín","B11",null,null,null,"ano",null,null,null,2.04,18.02129472,{"$nulls":5},"zpracovat PD a realizace"]
[409,null,"Cyklistická komunikace Chudobín - Nasobůrky","Litovel","Chudobín, Nasobůrky","B11",null,null,null,"ano",null,null,null,0.92,8.12725056,{"$nulls":5},"zpracovat PD a realizace"]
[{"$nulls":12},"součet délky v km",null,"součet nákladů v mil. Kč"]
[{"$nulls":12},335.4900000000003,null,2327.8177758360002]

{"sheet":"Olomouc","index":1,"n_rows":34,"n_cols":22,"rows_kept":34,"cut":false,"hidden":false,"merged":[[33,12,33,13],[33,14,33,16],[32,12,32,13],[32,14,32,16],[0,0,0,21]],"flags":["formulas_cached_only"]}
["Soupis připravených záměrů OLOMOUCE dle jednotlivých tras do roku 2018 s výhledem do roku 2022"]
[" č.","Trasa","Název akce","Obec","Katastrální území","Typ komunikace","ITI","IROP","SFDI","SPÚ","Lesy ČR","DUR / DSP","ST / IZ (pouze)","Délka          v km","Cena          mil. Kč         vč. DPH","Nákl. na  pozemky","Aktivita 2015","Aktivita 2016","Aktivita 2017","Aktivita 2018","Aktivita 2019-2022","Poznámka"]
["OL1","C13","Týneček - Chválkovice","Olomouc","Chválkovice","C9","ano","ano",null,null,null,"ano",null,0.636,7,null,"vydáno staveb.pov.Prodlužuje se do 04/2017. Akce je připravena k realizaci.","realizace",null,null,null,"Priorita KMČ Týneček"]
["OL2","B13","Trasa ul. Jeremenkova od Jantarové cyklotrasy po hl. n. ČD  ","Olomouc","Hodolany","C10","ano","ano",null,null,null,"ano",null,0.23,2.6,null,"zpracovává se  DPS - dokončit","realizace",null,null,null,"Bude připravena k realizaci"]
["OL3","B18","Trasa ul. Na Vozovce                     řešení zklidnění na zónu 30  ","Olomouc","Nová Ulice","V14+IP20","ano","ano",{"$nulls":4},"ano",0.665,11.5,null,"dokončit DSP","zpracovat DPS","realizace",null,null,"Radiální trasa Olomouc - Náměšť na Hané"]
["OL4","C6","Radiální trasa Olomouc – Chomoutov – vazba na Březce vč. propojky u betonárny","Olomouc","Černovír, Chomoutov","C9","ano","ano","ano",null,null,null,"ano",2.99,18.5,null,"zpracování DÚR","dokončení DÚR a zpracovat DSP+DPS","realizace",null,null,"Priorita KMČ, jeden z nejnebezpečnějších úseků. Priorita Štěpánova"]
["OL5","B13","Ul. Jeremenkova - II. část ","Olomouc","Olomouc - město","V14+IP20","ano","ano",{"$nulls":4},"ano",0.426,1,null,null,"zpracovat DSP+DPS","realizace",null,null,"Úsek od Jantarové stezky po křižovatku s ul Pasteurovou) (převážně vyhrazené cyklopruhy na místní komunikaci "]
["OL6","A2","Cyklostezka Holice – Keplerova – Holický les (ul. Šlechtitelů)","Olomouc","Holice u Olomouce","C9","ano","ano",null,null,null,"ano",null,1.956,25,null,"zpracovává se DSP+DPS","dokončit DSP+DPS","realizace"]
["OL7","A2","Propojení ul. Šlechtitelů a Přichystalovy","Olomouc","Holice u Olomouce","B11",null,null,null,"ano",null,null,null,0.76,6.713815680000001,null,null,"zpracovat DSP+DPS","realizace"]
["OL8","A2","Tangenciála - propojení ul. Dolní novosadská – ul. Šlechtitelů ","Olomouc","Nové Sady u Olomouce, Holice u Olomouce","C9","ano","ano","ano",null,null,null,"ano",1.25,7.5,null,"zpracovat DÚR","zpracovat DSP+DPS","realizace",null,null,"Návaznost na akci Holice – holický les, jedná se o nebezpečnou tangenciálu propojující dvě průmyslové zóny"]
["OL9","A1","Moravská Nemilany část 2","Olomouc","Nemilany","C9","ano","ano","ano",null,null,"ano",null,0.439,6.1,null,null,null,"aktualizovat DÚR a zpracovat DSP+DPS","realizace",null,"Úsek směrem na Kožušany –  církevní restituce - nutno prověřit stav - JUDR.Polcrová."]
["OL10","B18","Radiální trasa Olomouc Neředín -  Topolany - Ústín","Olomouc","Neředín, Topolany u Olomouce","C9","ano","ano","ano",null,null,null,"ano",2.66,11.3,null,null,"dokončit DÚR + zahájit zpracování DSP+DPS","dokončit DSP","realizace",null,"Vazba na již vybudovanou cyklostezku v Ústíně, která je do doby realizace naší akce jednosměrná. Priorita KMČ Topolany a obce Ústín."]
["OL11","B9","Cyklostezky v úseku ul. Tř.17.listopadu (od PřF UP) – ul.Husova (restaurace Bristol) ","Olomouc","Olomouc - město","C10","ano","ano","ano",null,null,null,"ano",0.65,5.4,null,null,"DÚR","DSP+DPS","realizace",null,"Priorita pracovní skupiny cyklodoprava, navazuje na most u Bristolu a na protipovodňová opatření"]
["OL12","B18","Třída Svobody - jízdní pruhy pro cyklisty","Olomouc","Olomouc - město","V14+IP20","ano","ano",{"$nulls":5},0.822,6.05126808,null,"studie","DÚR","DSP+DPS","realizace",null,"Priorita - město dobré pro život"]
["OL13","C20","Tangenciála Topolany - Hněvotín - Nedvězí","Olomouc","Nedvězí, Topolany u Olomouce","C9","ano","ano","ano",{"$nulls":4},1.403,10.328380919999999,null,null,"zpracovat IZ č. 21","zpracovat DÚR","zpracovat DSP+DPS","realizace","Důležitá tangenciála – spolupráce s obcí Hněvotín – je ochotna uhradit DÚR z vlastních zdrojů. Nutno nejdříve zpracovat IZ"]
["OL14","A2","Trasa od  kruhové křižovatky u Baumaxu na ul. Holické – Holice ul. Přerovská ","Olomouc","Hodolany, Holice u Olomouce","V14+IP20","ano","ano","ano",null,null,null,"ano",2.03,12.4,null,null,null,"zpracovat DÚR","zpracovat DSP+DPS","realizace","Převážně vyhrazené cyklopruhy na III/03551, nejvíce zatížená komunikace pohybem cyklistů a chodců"]
["OL15","C13","Tangenciála Samotišky – Droždín – Bystrovany","Olomouc","Droždín","C9","ano","ano","ano",null,null,null,"ano",1.928,14.19324192,null,null,null,"zpracovat DÚR","zpracovat DSP+DPS","realizace","Požadavek obou obcí a KMČ Droždín, která je údajně ochotna přispět na akci ze svého rozpočtuprůtah. Droždínem vyhrazené cyklopruhy na III/4436  "]
["OL16","A2","Cyklostezky v úseku teplárna Dalkia - úřad práce - Tř. Kosmonautů – ZUŠ na ul. Kavaleristů ","Olomouc","Hodolany","C10","ano","ano",{"$nulls":4},"ano",0.79,6.1,{"$nulls":4},"zpracovat DÚR","zpracovat PD a realizace"]
["OL17","B12","Trasa Řepčín souběh s tratí mimo ulici Svatoplukovu kolem Cyrilometodějského kostela po ul. Pražskou ","Olomouc","Řepčín","C9","ano","ano","ano",null,null,null,"ano",0.36,1.6,{"$nulls":4},"zpracovat DÚR","zpracovat PD a realizace","Koordinovat se záměrem SŽDC elektrifikace železniční trati."]
["OL18","B12","Cyklostezka v úseku Neředín sběrný dvůr - Globus + úsek podél ulice Křelovské směrem k žel. trati","Olomouc","Neředín, Řepčín","B11","ano","ano",null,null,null,"ano",null,1.593,14.072511023999999,{"$nulls":5},"zpracovat PD a realizace"]
["OL19","A1a","Cyklostezky v úseku Polská – Rooseveltova","Olomouc","Nové Sady u Olomouce, Olomouc - město","C10","ano","ano",{"$nulls":4},"ano",0.68,4.2,{"$nulls":5},"zpracovat PD a realizace","Obousměrná cyklostezka vedena v zeleném pásu"]
["OL20","B18","Cyklostezky v úseku ul. Okružní ","Olomouc","Nová Ulice, Neředín","V14+IP20","ano","ano",{"$nulls":4},"ano",2.985,5,{"$nulls":5},"zpracovat PD a realizace","Tangenciála na území města (včechny 3 druhy - cyklostezka, smíšená stezka, cyklopruhy)"]
["OL21","A1","Cyklostezky v úseku Baumax - Autobusové nádraží ","Olomouc","Hodolany","C9","ano","ano","ano",null,null,null,"ano",1.29,2,{"$nulls":5},"zpracovat PD a realizace"]
["OL22","A1","Cyklostezky v úseku ul. Jeremenkova / Fibichova – Ostravská  ","Olomouc","Hodolany","C9","ano","ano","ano",{"$nulls":4},0.72,2.4,{"$nulls":5},"zpracovat PD a realizace"]
["OL23","B18","Kmochova - Foersterova","Olomouc","Nová Ulice","V14+IP20","ano","ano",{"$nulls":4},"ano",0.22,3,{"$nulls":5},"zpracovat PD a realizace","Pokračování radiální trasy z ul. Na Vozovce a napojení se na smíšenou stezku v ul. Jílová budovanou z provozních prostředků OD"]
["OL24","B9","Bořivojova - Dlouhá – Morava (přes Lazce) ","Olomouc","Lazce","C10","ano","ano",{"$nulls":4},"ano",0.63,5.5,{"$nulls":5},"zpracovat PD a realizace","Navazuje na již vybudovanou radiálu Olomouc - Šternberk. V úseku Lazce - Černovír bude řešeno v rámci protipovodňových úprav Povodím Moravy."]
["OL25","A2a","Cyklostezky v úseku ul. Na Výsluní - Pavelkova (singletrack) ","Olomouc","Hodolany","C9","ano","ano",{"$nulls":4},"ano",0.21,0.5,{"$nulls":5},"zpracovat PD a realizace"]
["OL26","A2","Cyklostezky v úseku od Návsi Svobody  po ul. Průmyslovou v Holici + zóna 30 v ulicích k rybníku „Amerika“ ","Olomouc","Holice u Olomouce","C10","ano","ano",{"$nulls":4},"ano",0.41,2.7,{"$nulls":5},"zpracovat PD a realizace"]
["OL27","C6","Cyklopruhy - Moravská stezka na území ORP Olomouc, k.ú.Nová Ulice – ul.Legionářská","Olomouc","Nová Ulice","V14+IP20","ano","ano",{"$nulls":4},"ano",0.223,1.6,{"$nulls":5},"zpracovat PD a realizace","Poslední úsek Moravské stezky. bylo vydáno staveb. povolení ale propadlo a nebylo obnoveno, protože akce je nahrazena novou - Legionářská - Studentská, rekonstrukce komunikace; zde je zpracována DUR a DSP, obnovuje se ÚR, vydání SP je podmíněno vyřešením "]
["OL28",null,"Výstavby cyklostojanů","Olomouc",null,"Stojany","ano","ano",{"$nulls":6},5,null,null,"zpracovat dok. Pro ÚS + instalace 40 ks. stojanů","zpracovat dok. Pro ÚS + instalace 40 ks. stojanů","zpracovat dok. Pro ÚS + instalace 40 ks. stojanů","zpracovat PD a realizace"]
["OL29",null,"2ks Parkovací domy ","Olomouc",null,"Stojany","ano","ano",{"$nulls":6},14,null,null,"DSP+DPS","Instalace 1.park. Domu","Instalace 1.park. Domu"]
["OL30",null,"Parkovací boxy ","Olomouc",null,"Stojany","ano","ano",{"$nulls":6},2,null,null,"Dokumentace pro Územní souhlas","Instalace ","Instalace ","zpracovat PD a realizace"]
[{"$nulls":12},"součet délky v km",null,"součet nákladů v mil. Kč"]
[{"$nulls":12},28.955999999999996,null,215.25921762399994]

{"sheet":"Prostějov","index":2,"n_rows":18,"n_cols":22,"rows_kept":18,"cut":false,"hidden":false,"merged":[[0,0,0,21],[16,12,16,13],[16,14,16,16],[17,12,17,13],[17,14,17,16]],"flags":["formulas_cached_only"]}
["Soupis připravených záměrů PROSTĚJOVA dle jednotlivých tras do roku 2018 s výhledem do roku 2022"]
[" č.","Trasa","Název akce","Obec","Katastrální území","Typ komunikace","ITI","IROP","SFDI","SPÚ","Lesy ČR","DUR / DSP","ST / IZ (pouze)","Délka          v km","Cena          mil. Kč         vč. DPH","Nákl. na  pozemky","Aktivita 2015","Aktivita 2016","Aktivita 2017","Aktivita 2018","Aktivita 2019-2022","Poznámka"]
["PV1","C1","CS Žešov IV. etapa","Prostějov","Prostějov","C9","ano","ano","ano",null,null,"ano",null,0.81,3.2,null,"majetkoprávní řešení","realizace"]
["PV2","C1","CS Žešov V. etapa","Prostějov","Žešov","C9","ano","ano","ano",null,null,"ano",null,0.44,1.7,null,"majetkoprávní řešení","majetkoprávní řešení","realizace"]
["PV3","C1","CS Okružní (úsek Šárka)","Prostějov","Prostějov","C9","ano","ano",null,null,null,"ano",null,0.58,2.3,null,null,null,"realizace"]
["PV4","C1","CS Okružní (úsek Brněnská - Jezdecká)","Prostějov","Prostějov",null,"ano","ano",null,null,null,"ano",null,0.59,4.5,null,"DÚR, DSP",null,"majetkoprávní řešení",null,"realizace"]
["PV5","A1","CS Vrahovická","Prostějov","Prostějov","V14+IP20","ano","ano","ano",null,null,null,"ano",1.12,15,null,"DÚR","DSP",null,null,"realizace","zahrnuje 2 mostní objekty"]
["PV6","C2","CS Určická I. etapa","Prostějov","Prostějov","C9","ano","ano","ano",null,null,"ano",null,0.96,4.1,null,null,"majetkoprávní řešení","majetkoprávní řešení","majetkoprávní řešení","zpracovat PD a realizace","majektoprávně náročné"]
["PV7","C2","CS Určická II. etapa","Prostějov","Žešov","C9","ano","ano","ano",null,null,null,"ano",0.85,5,null,"DÚR",null,null,null,"zpracovat PD a realizace"]
["PV8","C2","CS Určická III. etapa","Prostějov","Žešov","C9","ano","ano","ano",null,null,null,"ano",0.57,3,null,null,"DÚR, DSP","majetkoprávní řešení","majetkoprávní řešení","zpracovat PD a realizace","majektoprávně náročné"]
["PV9","C3","CS Anglická Holandská","Prostějov","Prostějov","C10","ano","ano",null,null,null,"ano",null,0.21,1.2,null,null,"realizace"]
["PV10","B1","CS Kostelecká","Prostějov","Prostějov","C10","ano","ano","ano",null,null,"ano",null,0.62,2.7,null,"DÚR","DSP","realizace"]
["PV11","C3","CS Plumlovská (úsek Legionářská - Domamyslice)","Prostějov","Prostějov, Čechovice u Prostějova, Domamyslice","V14+IP20","ano","ano","ano",null,null,null,"ano",0.97,3.4,{"$nulls":4},"DÚR","zpracovat PD a realizace"]
["PV12","A3a","CS Průmyslová","Prostějov","Prostějov","C9","ano","ano",{"$nulls":4},"ano",0.97,4.1,{"$nulls":5},"zpracovat PD a realizace"]
["PV13","A1","CS Říční","Prostějov","Prostějov","C8","ano","ano",{"$nulls":4},"ano",0.96,6.1,null,"DÚR, DSP",null,null,null,"zpracovat PD a realizace"]
["PV14","C3","CS J. Lady","Prostějov","Čechovice u Prostějova, Krasice","C10","ano","ano","ano",null,null,null,"ano",0.25,2.3,{"$nulls":5},"zpracovat PD a realizace"]
[{"$nulls":12},"součet délky v km",null,"součet nákladů v mil. Kč"]
[{"$nulls":12},9.899999999999999,null,58.6]

{"sheet":"Přerov","index":3,"n_rows":25,"n_cols":22,"rows_kept":25,"cut":false,"hidden":false,"merged":[[0,0,0,21],[23,12,23,13],[23,14,23,16],[24,12,24,13],[24,14,24,16]],"flags":["formulas_cached_only"]}
["Soupis připravených záměrů PŘEROVA dle jednotlivých tras do roku 2018 s výhledem do roku 2022"]
[" č.","Trasa","Název akce","Obec","Katastrální území","Typ komunikace","ITI","IROP","SFDI","SPÚ","Lesy ČR","DUR / DSP","ST / IZ (pouze)","Délka          v km","Cena          mil. Kč         vč. DPH","Nákl. na  pozemky","Aktivita 2015","Aktivita 2016","Aktivita 2017","Aktivita 2018","Aktivita 2019-2022","Poznámka"]
["PR1","A2a","Propojení cyklostezky Velká Dlážka - Hranická","Přerov",null,"C8",{"$nulls":6},"ano",0.25,14.5,{"$nulls":4},"realizace",null,"Podjezd pod tratí"]
["PR2","A2","Cyklostezka Velká Dlážka","Přerov",null,"C10",{"$nulls":5},"ano",null,0.7,8.58858,null,null,null,"realizace"]
["PR3","C15","Cyklostezka Přerov - Čekyně - Penčičky","Přerov","Předmostí, Čekyně, Penčičky","C9","ano","ano","ano",null,null,null,"ano",4.219,24.847007327999997,{"$nulls":4},"realizace"]
["PR4","C18","Smíšená stezka Přerov - Horní Moštěnice","Přerov","Újezdec u Přerova","C9","ano","ano","ano",{"$nulls":4},1.37,13.447262400000001,{"$nulls":5},"zpracovat PD a realizace"]
["PR5","C18","Jízdní pruhy, ul. 9 května","Přerov","Přerov","V14+IP20","ano","ano","ano",{"$nulls":4},0.945,6.956749800000001,{"$nulls":5},"zpracovat PD a realizace"]
["PR6","C18","Dělená stezka Šírava - Ztracená","Přerov","Přerov","C10","ano","ano",{"$nulls":5},0.732,5.747968511999999,{"$nulls":5},"zpracovat PD a realizace"]
["PR7","C17","Dělená stezka Želatovská","Přerov","Přerov","C10","ano","ano","ano",{"$nulls":4},0.451,3.5414396159999995,{"$nulls":5},"zpracovat PD a realizace"]
["PR8","C17","Dělená stezka Dvořákova","Přerov","Přerov","C10","ano","ano","ano",{"$nulls":4},0.697,5.4731339519999995,{"$nulls":5},"zpracovat PD a realizace"]
["PR9","B16","Propojení Tovačovská - Mádrův podjezd","Přerov","Přerov","C9","ano","ano",{"$nulls":5},1.204,8.86341456,{"$nulls":5},"zpracovat PD a realizace"]
["PR10","A3","Dělená stezka Husova k nádraží","Přerov","Přerov","C10","ano","ano","ano",{"$nulls":4},0.373,2.9289511679999998,{"$nulls":5},"zpracovat PD a realizace"]
["PR11","A2","Smíšená stezka Dluhonice - Předmostí","Přerov","Dluhonice, Přerov","C9","ano","ano","ano",{"$nulls":4},1.996,14.69383344,{"$nulls":5},"zpracovat PD a realizace"]
["PR12","A2","Dluhonice - křížení s tratí","Přerov","Přerov","Lávka","ano","ano","ano",{"$nulls":4},0.1,10,{"$nulls":5},"zpracovat PD a realizace"]
["PR13","B15","Smíšená stezka \"Průpich\"","Přerov","Přerov","C9","ano","ano",{"$nulls":5},0.38,2.7974232000000008,{"$nulls":5},"zpracovat PD a realizace"]
["PR14","B15","Smíšená stezka Velké Novosady - Komenského","Přerov","Přerov","C9","ano","ano",{"$nulls":5},0.236,1.73734704,{"$nulls":5},"zpracovat PD a realizace"]
["PR15","B15","Smíšená stezka Polní","Přerov","Přerov","C9","ano","ano","ano",{"$nulls":4},0.981,7.221768840000001,{"$nulls":5},"zpracovat PD a realizace"]
["PR16","B15","Smíšená stezka Lipnická","Přerov","Přerov","C9","ano","ano","ano",{"$nulls":4},0.92,6.772708800000001,{"$nulls":5},"zpracovat PD a realizace"]
["PR17","B15","Smíšenás tezka Lýsky","Přerov","Popovice u Přerova, Lýsky","C9","ano","ano","ano",{"$nulls":4},0.986,5.806861632,{"$nulls":5},"zpracovat PD a realizace"]
["PR18","B15","Cyklistická komunikace Prosenice - Lýsky","Přerov","Lýsky","C9","ano","ano","ano",{"$nulls":4},0.487,3.5851186799999994,{"$nulls":5},"zpracovat PD a realizace"]
["PR19","B15","Cyklistická komunikace Prosenice - Lýsky","Přerov","Lýsky","B11",null,null,null,"ano",null,null,null,0.51,4.50532368,{"$nulls":5},"zpracovat PD a realizace"]
["PR20","C15","Jízdní pruhy ul. Palackého","Přerov","Přerov","V14+IP20","ano","ano","ano",{"$nulls":4},0.196,0.35574000000000006,{"$nulls":5},"zpracovat PD a realizace"]
["PR21","C15","Dělená stezka ul. Palackého","Přerov","Přerov","C10","ano","ano","ano",{"$nulls":4},0.493,4.839051359999999,{"$nulls":5},"zpracovat PD a realizace"]
[{"$nulls":12},"součet délky v km",null,"součet nákladů v mil. Kč"]
[{"$nulls":12},18.226000000000003,null,157.209684008]

{"sheet":"Suma nákladů","index":4,"n_rows":6,"n_cols":5,"rows_kept":6,"cut":false,"hidden":false,"merged":[[0,4,4,4]],"flags":["formulas_cached_only"]}
[null,"v mil. Kč vč. DPH","Dotace 85%","Délka v km","Průměrné náklady na km v mil. Kč vč. DPH"]
["Olomouc",215.25921762399994,182.97033498039994,28.955999999999996]
["Prostějov",58.6,49.81,9.899999999999999]
["Přerov",157.209684008,133.6282314068,18.226000000000003]
["Ostatní",2327.8177758360002,1978.6451094606002,335.4900000000003]
[null,2758.886677468,2345.0536758478,392.5720000000003,7.027721481582991]

{"sheet":"Jednotkové náklady","index":5,"n_rows":15,"n_cols":6,"rows_kept":15,"cut":false,"hidden":false,"merged":[[1,4,1,5],[1,2,1,3],[11,2,11,3],[11,4,11,5]],"flags":["formulas_cached_only"]}
["Typy cyklistických komunikací",null,"Kč/m2 bez DPH","Kč/m2 vč. DPH","Kč/m2 bez DPH","Kč/m2 vč. DPH"]
[null,null,"extravilán",null,"intravilán"]
["C8","Stezka pro cyklisty",1622.3999999999999,1963.1039999999998,2028,2453.88]
["C9","Stezka pro chodce a cyklisty se společným provozem",1622.3999999999999,1963.1039999999998,2028,2453.88]
["C10","Stezky pro chodce a cyklisty s odděleným provozem",1622.3999999999999,1963.1039999999998,2028,2453.88]
["C7+E13","Stezky pro chodce s povoleným vjezdem cyklistů",null,null,2028,2453.88]
["B11","Komunikace s vyloučeným motorové dopravy",2433.6,2944.656]
["NIC","Silnice II. A III. s minimálním dopravním zatížením",0,0]
["IP25","Zklidněná komunikace - Zóna 30",2433.6,2944.656]
["IP26","Obytná zóna",2433.6,3271.8399999999997]
["E12","Obousměrný provoz cyklistů v jednosměrných komunikacích",null,0]
[null,null,"jednoduchá úprava",null,"vč. Konstrukce"]
["V20","Piktogramové koridory pro cyklisty",500,605,2028,2453.88]
["V14+IP20","Vyhrazené jídní pruhy pro cyklisty",500,605,2028,2453.88]
["Realiz.","Zrealizovaná cyklistická komunikace"]